## Sheet1
Job # | Name/Rel. | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Panels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
2019-12-30
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1651 | The Bristol | MS-67 | C Barter | NO | NO | 1 | 4 | [10 empty] | 1 | 2019-12-30 | 2019-12-31 |  | 1 | Shipped | 7948 | Andrey Picked up
1811 | State Farm Park Center Phase II | MS-17 A | M Persons | NO | NO | 1 | 540 | [10 empty] | 68 | 2019-12-30 | 2019-01-13 |  |  | Shipped | 7948
1873 | Reston Office Bldg 3 | LVR-01 | K Burgess | NO | NO | 4 |  | 290 | [9 empty] | 73 | 2020-09-19 | 2020-10-20 |  |  | Shipped | Site | completion of Original release (Flashing Portion)
1874 | Twelve24 | MS-SS-25 | T Messer | NO | NO | 5 |  | 136 | [9 empty] | 34 | 2019-12-16 | 2019-12-18 |  | 2 | Shipped | 7948 | waiting on material
1874 | Twelve24 | MS-SS-26 | T Messer |  |  |  | 70 | [10 empty] | 17 | 2019-12-31 | 2019-01-03 |  |  | Shipped | 7948
1898 | Avalon 10000 | MS-07 | A York | NO | NO | 1 | 24 | [10 empty] | 6 | 2020-01-02 | 2020-01-02 | 2020-01-07 | 0 | Shipped | 7948
17103 | The Boro - A3 | MS-19 | C Tucker | NO | NO | 4 |  | 40 | [9 empty] | 10 | 2019-12-27 | 2019-01-07 | 2020-01-08 |  | Shipped | 7948
18104 | Garco Mill Entertainment | MCM-3B | C Jaunsen | YES | NO | 1 | [8 empty] | 200 |  |  |  | 2020-12-29 | 2020-01-05 | 2020-01-02 |  | Shipped | 7948
19042 | 1300 4th Street NE | MS-2 | C Whitehorne | NO | 3256 | 4 | 16 | 6 | [9 empty] | 4 | 2019-12-16 | 2019-01-06 |  | 1/6 | Shipped | FD
19042 | 1300 4th Street NE | PAP-MU-1 | C Whitehorne | YES | 3022 | 9 | [6 empty] | 9 |  |  |  |  | 230 | 2019-12-16 | 2019-01-06 |  | 1/6 | Shipped | FD
[6 empty] | 30 | 654 | 472 | 0 | 0 | 0 | 0 | 9 | 0 | 200 | 0 | 0 | 443
2020-01-06
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Panels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1730 | Reston Hospital Ctr | MS-2 | S Hadley | NO | NO | 4 | 37 | [7 empty] | 24 |  |  | 4 | 2020-12-31 | 2020-01-14 | 2020-01-08 |  | Shipped | 7948
1773 | The GEO Group Corporate HDQ | CO Trim | G Samples | NO | NO | 1 |  | 3 | [9 empty] | 1 | 2020-01-09 | 2020-01-09 | 2020-01-09 |  | Shipped | Site
1796 | 4040 Wilson Blvd | MS-21 | S Orell | NO | NO | 2 | [11 empty] | 1 | 2020-01-03 | 2020-01-08 | 2020-01-09 |  | Shipped | 7948
1811 | State Farm Park Center Phase II | MS-04A | T Messer | YES | NO | 1 | 72 | [10 empty] | 9 | 2020-01-07 | 2020-01-14 | 2020-01-09 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | AD-MS-1 | K Burgess | NO | NO | 9 | 811 | [10 empty] | 102 | 2019-12-30 | 2019-01-13 | 2020-01-10 |  | Shipped | 7948 | Revision effected material usages and shop time.
1873 | Reston Office Bldg 3 | PAP-6 | K Burgess | YES | NO | [7 empty] | 14 |  |  |  |  | 91 | 2020-12-19 | 2020-01-10 | 2020-01-10 |  | Shipped | 7948 | Correct Release date 12/30 Panels are punched/formed and awaiting extrusion attachment 1/6
1874 | Twelve24 | MS-33.1 | T Messer | NO | NO | 1 |  | 15 | [9 empty] | 4 | 2020-01-07 | 2020-01-09 | 2020-01-08 |  | Shipped | Site | Tom picked up from shop
1874 | Twelve24 | MCM-SS-27 | T Messer | NO | NO | 2 | 50 | 30 | [9 empty] | 15 | 2020-01-09 | 2020-01-10 | 2020-01-10 |  | Shipped | 7948
1883 | 1050 17th Street | Parts | S Hadley | NO | NO | 1 |  |  | 8 | [8 empty] | 3 | 2020-01-07 | 2020-01-07 | 2020-01-09 |  | Shipped | Site
1883 | 1050 17th Street |  | S Hadley | NO | NO |  | 8 | [10 empty] | 1 | 2020-01-06 | 2020-01-06 | 2020-01-06 |  | Shipped | 7948
1898 | Avalon 10000 | MS-9 | A York | NO | NO | 1 | 24 | [10 empty] | 3 | 2020-01-08 | 2020-01-08 | 2020-01-08 |  | Shipped | Site
1898 | Avalon 10000 | MS-5 REMAKE | A York | NO | NO | 2 |  | 26 | [9 empty] | 6 | 2020-12-12 | 2020-12-16 | 2020-01-08 |  | Shipped | Site | remake these parts were make and shipped to 7948 on 12/13 mislocated.. Undocumented after leaving 8005
1898 | Avalon 10000 | MS-8 | A York | NO | NO | 2 | 155 | [10 empty] | 19 | 2020-01-06 | 2020-01-07 | 2020-01-07 |  | Shipped | Site | Partial order shipped 1/7 to site remaining balance is ready 1/7
1898 | Avalon 10000 | MS-10 | A York | NO | NO | 10 |  | 44 |  | 5 | [7 empty] | 12 | 2020-01-08 | 2020-01-09 | 2020-01-09 |  | Shipped | Site
1898 | Avalon 10000 | MS-11 | J Johns | NO | NO | 1 | 24 | [11 empty] | 2020-01-09 | 2020-01-09 | 2020-01-09 |  | Shipped | Site
18103 | Moving in the Spirit | MS-7 | A York | NO | NO | 4 |  | 60 |  | 20 | [7 empty] | 20 | 2020-01-06 | 2020-01-07 | 2020-01-09 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-2 | S Orrell | YES | NO | 10 |  | 40 | [9 empty] | 10 | 2020-01-07 | 2020-01-13 |  |  | Shipped | 7948 | Waiting on Material to deliver( rec'd 1/9)
18123 | Penn State Heister Street | FCP-1B | K Burgess | No | 3289 | 8 |  | 52 | [9 empty] | 13 | 2020-12-13 | 2020-01-27 | 2020-01-06 |  | Shipped | FD | Correct release date 12/30
[6 empty] | 59 | 1181 | 270 | 8 | 25 | 0 | 0 | 14 | 0 | 24 | 0 | 0 | 314
2020-01-13
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1873 | Reston Office Bldg 3 | PAP-2 | K Burgess | YES | NO | [7 empty] | 138 |  |  |  |  | 690 | 2020-12-12 | 2020-01-06 | 2020-01-15 |  | Shipped | 7948 | several changes were required new release date 1/2/2020. Panels are punched and formed. All releases "Blonde Pear" are on hold pending color approval per Greg. 1/7
1873 | Reston Office Bldg 3 | PAP-7 | K Burgess | NO | NO | 4 | [6 empty] | 133 |  |  |  |  | 798 | 2019-12-19 | 2019-01-22 | 2020-01-17 |  | Shipped | Site | Correct release date 12/30…expected completion date 1/17
1873 | Reston Office Bldg 3 | MS-07 | K Burgess | NO | NO | 1 |  | 10 | [9 empty] | 4 | 2020-01-15 | ASAP | 2020-01-17 |  | Shipped | 7948
1874 | Twelve24 | MS-SS-40 | T Messer | NO | NO | 3 |  | 42 | [9 empty] | 10 | 2020-01-13 | 2020-01-13 | 2020-01-13 |  | Shipped | Site
1898 | Avalon 10k | MS-13 | J Johns | NO | NO | 1 | 10 | [10 empty] | 2 | 2020-01-17 | ASAP | 2020-01-17 |  | Shipped | Site | Ken Pitts picked up
18104 | Garco Mill Entertainment | MS-02 | C Jaunsen | NO | NO | 4 | 510 | 93 | [9 empty] | 87 | 2020-01-09 | 2020-01-17 | 2020-01-17 |  | Shipped | 7948
18123 | Penn State Heister Street | FCP-1A | K Burgess | NO | 3262 | 18 |  | 227 | [9 empty] | 57 | 2020-12-13 | 2019-01-27 | 2020-01-20 |  | Shipped | FD | Correct release date 12/30
19047 | Project Charisma | MS-01 | C Jaunsen | NO | NO | 4 |  | 26 | [9 empty] | 6 | 2020-01-09 | 2020-01-17 | 2020-01-17 |  | Shipped | 7948
[6 empty] | 35 | 520 | 398 | 0 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 1654
2020-01-20
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1874 | Twelve24 | MS-SS-51 | T Messer | NO | NO | 1 |  | 11 | [9 empty] | 3 | 2020-01-21 | 2020-01-28 |  |  | Shipped | 7948
1898 | Avalon 10k | MS-12 | J Johns | NO | NO | 6 | 66 |  | 57 | [8 empty] | 29 | 2020-01-14 | 2020-01-20 |  |  | Shipped | 7948
1898 | Avalon 10000 | MS-15 | J Johns | NO | NO | 3 |  | 10 | [9 empty] | 3 | 2020-01-20 | 2020-01-21 |  |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-4 | S.Orell | YES | NO | 3 | 1900 | [10 empty] | 180 | 2020-01-17 | 2020-01-20 | 2020-01-20 |  | Shipped | Site
19012 | Hyatt PL Perimeter Mall | MS-01 | J Howard | NO | NO | 2 | 365 | [10 empty] | 45 | 2020-01-23 | 2020-01-28 |  |  | Shipped | 7948
19041 | WPUSD - Twelve Bridges HS | MU | S.Wright | NO | NO | NA | [10 empty] | 20 | 4 |  |  |  |  | Shipped | 7948
19085 | Bellyard at the Interlock | MS-MU-1 | N Dowd | NO | NO | 1 |  | 1 | [9 empty] | 1 | 2020-01-22 | 2020-01-24 |  |  | Shipped | Site
[6 empty] | 16 | 2331 | 22 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 265
2020-01-27
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1744 | Ripley East | MS-15 | G Espinell | YES | NO | 3 | 15 | 25 | [9 empty] | 7 | 2020-01-27 | 2020-02-03 | 2020-01-31 |  | Shipped | 7948
1796 | 4040 Wilson Blvd | MS-11REV | S.Orell | NO | NO | 7 |  | 144 | [9 empty] | 24 | 2020-01-24 | 1899-12-31 06:14 |  |  | Shipped | 7948
1811 | State Farm Park Center Phase II | MS-SS-LB1 | T Messer | NO | NO | 5 | 28 | 24 | [9 empty] | 9 | 2020-01-29 | 2020-02-03 | 2020-02-04 |  | Shipped | 7948
1833 | University of Maryland | MS-04 | J Howard | NO | NO | 3 |  | 61 | [9 empty] | 15 | 2020-01-28 | 2020-02-03 |  |  | Shipped | 7948
1873 | Reston Office Bldg 3 | MS-08 | K Burgess | NO | 3388 | 3 |  | 12 | [9 empty] | 3 | 2020-01-22 | 2020-01-24 | 2020-01-30 |  | Shipped | FD | Further details are needed regarding Item 3 it is on hold until those detailer regarding material type are clear and final. Details resolved partial shipment made to site. Balance awaiting shipment to F.D
18123 | Penn State Heister Street | MP-1A | K Burgess | NO | 3261 | 23 |  | 882 | [9 empty] | 220 | 2019-12-30 | 2019-01-27 |  |  | Shipped | 7948 | Correct release date 12/30 there are 347 remaining pieces of Flashing that need to be sheared and formed, it will also be ready to ship by 1/29
18123 | Penn State Heister Street | MP-1B | K Burgess | NO | 3257 | 17 |  | 199 | [9 empty] | 50 | 2020-12-13 | 2019-01-27 | 2020-01-30 |  | Shipped | FD | Correct release date 12/30 Is about halfway through production it should be ready to ship to FD by 1/29, Revisions made on 1/23 to have FD paint several flashing on both sides.
19006 | Georgia Aquarium 2020 Exp | MS-4REV | S.Orell | NO | NO | 3 |  |  |  | 47 | [7 empty] | 4 | 2020-01-27 | 2020-01-29 | 2020-03-31 |  | Shipped | 7948
19012 | Hyatt PL Perimeter Mall | MS-02 | J Howard | NO | NO | 1 |  | 10 | [9 empty] | 3 | 2020-01-29 | 2020-01-31 | 2020-01-31 |  | Shipped | Site
19054 | Tift RMC-ED & Patient Twr | MS-05 | C Jaunsen | NO | NO | 4 | 8 | 2 | [9 empty] | 10 | 2020-12-26 | 2020-01-13 |  |  | Shipped | 7948
19060 | Dadeland Mall W Kendall | Ang | C Whitehorne | NO | NO | 2 | 21 | [10 empty] | 3 | 2020-01-29 | 2020-01-29 |  |  | Shipped | 7948
[6 empty] | 71 | 72 | 1359 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 348
2020-02-03
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1771 | MD Project | MS-18 | M Kunz | NO | NO | 1 | 95 | [10 empty] | 12 | 2020-01-30 | 2020-02-07 | 2020-02-05 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | PAP-6a | K Burgess | NO | NO | [7 empty] | 1 |  |  |  |  | 6 | 2020-12-19 | 2020-01-10 | 2020-02-04 |  | Shipped | 7948 | HOLD awaiting revised release ON HOLD until further notice
1873 | Reston Office Bldg 3 | PAP-8a | K Burgess | NO | NO | [7 empty] | 2 |  |  |  |  | 14 | 2020-12-19 | 2020-01-22 |  |  | Shipped | 7948 | HOLD awaiting revised release ON HOLD until further notice revisons were given on 1/23 releases is now ready for production
1873 | Reston Office Bldg 3 | PAP-5 | K Burgess | YES | NO | [7 empty] | 204 |  |  |  |  | 1224 | 2020-12-19 | 2020-01-31 |  |  | Shipped | 7948 | HOLD awaiting revised release ON HOLD until further notice. Revised releases received 1/7
1873 | Reston Office Bldg 3 | PAP-5a | K Burgess | NO | NO | [7 empty] | 5 |  |  |  |  | 28 | 2020-12-19 | 2020-01-22 |  |  | Shipped | 7948 | HOLD awaiting revised release ON HOLD until further notice Revised releases received and approved by Jason 1/7
1873 | Reston Office Bldg 3 | PAP-8 | K Burgess | YES | NO | [7 empty] | 53 |  |  |  |  | 318 | 2020-12-19 | 2020-01-24 |  |  | Shipped | 7948 | HOLD awaiting revised release ON HOLD until further notice. Final revisions received and approved by Jason 1/7
1874 | Twelve24 | MS-SS-50 | T Messer | NO | NO | 3 | 9 | 21 | [9 empty] | 28 | 2020-01-21 | 2020-01-28 | 2020-02-04 |  | Shipped | 7948
1898 | Avalon 10000 | MS-14 | J Johns | NO | NO | 1 | 24 | [10 empty] | 3 | 2020-01-20 | 2020-01-21 | 2020-02-05 |  | Shipped | Site
17103 | The Boro - A3 | PAP-09 | C Tucker | NO | 3287 | 4 | [6 empty] | 4 |  |  |  |  | 28 | 2020-01-08 | 2020-01-24 | 2020-02-05 |  | Shipped | FD
17103 | The Boro - A3 | PAP-01A | C Tucker | NO | NO | 2 | [6 empty] | 2 |  |  |  |  | 14 | 2020-01-13 | 2020-01-31 | 2020-02-05 |  | Shipped | FD
17103 | The Boro - A3 | PAP-9R | C Tucker | NO | 3287 | 1 | [6 empty] | 1 |  |  |  |  | 1 | 2020-01-23 | 2020-01-24 | 2020-02-05 |  | Shipped | FD
18104 | Garco Mill Entertainment | MS-04 | C Jaunsen | No | No | 1 | 12 | [10 empty] | 2 | 2020-02-04 | 2020-02-11 | 2020-02-04 |  | Shipped | 7948
18123 | Penn State Heister Street | ZH-01 | K Burgess | NO | NO | 9 | 6316 | [7 empty] | 4378 |  |  | 315 | 2020-12-13 | 2020-01-27 | 2020-02-07 |  | Shipped | Site | Correct release date 12/ has a remainder of 3000 HATS that need to be formed, 222 Flat Straps that need shearing and this is expected to be completed by 2/5 ( we can ship what we have ready if needed.)Hat Chanels completed on 2/27
18123 | Penn State Heister Street | MS-01 | K Burgess | NO | NO |  | 76 | [10 empty] | 19 | 2020-02-07 | 2020-02-07 | 2020-02-07 |  | Shipped | Site
19006 | Georgia Aquarium 2020 Exp | MS-6 | S Orell | YES | NO | 3 | 20 | 32 | [9 empty] | 11 | 2020-01-31 | 2020-02-03 | 2020-02-04 |  | Shipped | Site
19047 | Project Charisma | MS-02 | C. Jaunsen | NO | NO | 1 | [8 empty] | 120 |  |  | 4 | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | Shipped | 7948
[6 empty] | 26 | 6552 | 53 | 0 | 0 | 0 | 0 | 272 | 0 | 4498 | 0 | 0 | 2027
2020-02-10
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1651 | The Bristol | MS-68 | C Barter | NO | NO | 1 |  | 14 | [9 empty] | 4 | 2020-02-06 | 2020-02-06 | 2020-02-14 |  | Shipped | 7948
1786 | 45 L Street | MS-04 | E Lizardi | NO | NO | 1 | 1 | [10 empty] | 1 | 2020-02-05 | 2020-02-20 | 2020-02-14 |  | Shipped | 7948
1798 | Central Records Complex | MS-5R | S Hadley | YES | NO | 1 |  | 10 | [9 empty] | 3 | 2020-02-11 | 2020-02-24 | 2020-02-18 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | PAP-3 | K Burgess | YES | NO | [7 empty] | 234 |  |  |  |  | 1170 | 2020-12-19 | 2020-01-24 |  |  | Shipped | 7948 | HOLD awaiting revised release ON HOLD until further notice revisons were given on 1/23 releases is now ready for production
1873 | Reston Office Bldg 3 | MS-09 | K Burgess | NO | 3396 | 8 |  | 60 | [9 empty] | 15 | 2020-01-22 | 2020-02-10 | 2020-02-11 |  | Shipped | 7948
1883 | 1050 17th Street | MS-4 | S Hadley | NO | NO | 7 | 319 | 167 | [6 empty] | 30 |  |  | 82 | 2020-02-06 | 2020-02-14 | 2020-02-13 |  | Shipped | 7948 | Priority parts are ready for pick up 2/12
1888 | East Forest Park Library | MS-01 | M Kunz | NO | NO | 1 | 117 | [10 empty] | 15 | 2020-01-29 | 2020-02-12 | 2020-02-17 |  | Shipped | Site
19006 | Georgia Aquarium 2020 Exp | MS-9 | S Orell | NO | NO | 2 |  | 440 | [9 empty] | 110 | 2020-02-12 | 2020-02-19 |  |  | Shipped
19030 | 1105 West P'Tree Office | MU-2 | G Espinell | YES | 3425 | 7 | 21 | [5 empty] | 7 | [5 empty] | 2020-02-03 | 2020-02-12 | 2020-02-24 |  | Shipped | FD
19034 | Hyatt Place Titusville | MS-3 | N Dowd | NO | NO | 1 |  | 3 | [9 empty] | 1 | 2020-02-12 | 2020-02-14 | 2020-02-14 |  | Shipped | 7948
19082 | Gulfstream | MS-6 Rev | S Orell | NO | No | 2 | 24 | [10 empty] | 3 | 2020-02-05 | 2020-02-11 | 2020-02-14 |  | Shipped | 7948
[6 empty] | 31 | 482 | 694 | 0 | 0 | 0 | 0 | 241 | 0 | 30 | 0 | 0 | 1404
2020-02-17
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1859 | MCCNO Linear Park | MS-13 | M.Jacobson | NO | NO | 2 | 1665 | [10 empty] | 225 | 2020-01-17 | 2020-02-17 | 2020-02-26 |  | Shipped | Site
1869 | Bank of the Ozarks HQ | MS-2 | T Perry | NO | NO | 2 | 60 | [10 empty] | 8 | 2020-02-13 | 2020-02-17 | 2020-02-25 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | MS-10 | K Burgess | NO | 3397 | 3 |  | 24 | [9 empty] | 6 | 2020-02-07 | 2020-02-10 | 2020-02-18 |  | Shipped | FD | Unpainted Portion was sent to 7948 painted sent on 2/24
1898 | Avalon 10000 | MS-16 | J Johns | NO | NO | 2 | 10 | 3 | [9 empty] | 3 | 2020-02-13 | 2020-02-21 | 2020-02-26 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-5 | S Orell | YES | NO | 5 | 1300 | 640 | [9 empty] | 285 | 2020-01-30 | 2020-02-05 | 2020-02-18 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-7 | S Orell | YES | NO | 2 | 360 | [10 empty] | 45 | 2020-02-10 | 2020-02-17 |  |  | Shipped | Site
19012 | Hyatt PL Perimeter Mall | MS-2 | J Howard | NO | NO | 1 | 600 | [10 empty] | 150 | 2020-02-13 | 2020-02-18 | 2020-02-17 |  | Shipped | Site
19042 | 1300 4th Street NE | PAP-3 | C. Whitehorn | YES | 3392 | 46 | [6 empty] | 48 |  |  |  |  | 240 | 2020-02-12 | 2020-03-25 |  |  | Shipped | FD | punched 2/15 forming now
19061 | Rosslyn City Center | MS-1 | M Jacobson | NO | NO | 2 | 2800 |  | 9 | [8 empty] | 330 | 2020-01-29 | 2020-02-24 | 2020-05-29 |  | Shipped | Site
[6 empty] | 65 | 6795 | 667 | 9 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 1292
2020-02-24
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1859 | MCCNO Linear Park | MS-14 | M Jacobson | NO | NO | 1 |  | 100 | [9 empty] | 25 | 2020-02-17 | 2020-02-26 | 2020-02-26 |  | Shipped | Site
1883 | 1050 17th Street | PAP-3 | S Hadley | YES | 3426 | 22 | [6 empty] | 22 |  |  |  |  | 12 | 2020-02-19 | 2020-03-13 | 2020-03-03 |  | Shipped | FD
1883 | 1050 17th Street | MS-5 | S Hadley | NO | NO | 2 |  | 2 | [9 empty] | 1 | 2020-02-19 | 2020-02-21 | 2020-02-20 |  | Shipped | 7948 | Flashing shipped on 2/.20.2020
1883 | 1050 17th Street | MS-6 | S Hadley | NO | NO | 0 | [10 empty] | 4 | 1 | 2020-02-24 | 2020-02-25 | 2020-03-16 |  | Shipped | 7948
18104 | Garco Mill Entertainment | MS-5 | C Jaunsen | NO | NO | 7 | 140 | 44 | [9 empty] | 23 | 2020-02-18 | 2020-02-25 | 2020-02-27 |  | Shipped | 7948
19042 | 1300 4th Street NE | MS-3 | C Whitehorne | NO | 3496 | 3 | 55 | 12 | [9 empty] | 20 | 2020-02-19 | 2020-03-25 |  |  | Shipped | FD | Painted portion shipped to FD on 2/24 REMAINDER SHIPPED 3/27
[6 empty] | 35 | 195 | 158 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 4 | 82
March 2,2020
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1771 | MD Project | MS-19 | M Kunz | NO | NO | 1 | 600 | [10 empty] | 75 | 2020-02-27 | 2020-03-02 | 2020-03-04 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | MS-11 | K Burgess | NO | 3596 | 3 |  |  | 165 | [8 empty] | 42 | 2020-02-20 | 2020-03-16 | 2020-05-22 |  | Shipped | 7948 | On Hold per PM 2/25 SHIPPED TO FD 3/18 TO SITE 5/26
19006 | Georgia Aquarium 2020 Exp | MS-8 | S Orrell | NO | NO | 3 | 30 |  | 52 | [8 empty] | 17 | 2020-02-26 | 2020-03-04 | 2020-03-10 |  | Shipped | Site
19036 | Phipps Plaza Anchor | MS-1 | M Persons | NO | NO | 2 |  | 4 | [9 empty] | 1 | 2020-03-03 | 2020-03-06 | 2020-03-05 |  | Shipped | 7948
19047 | Project Charisma | MS-3 | C Jaunsen | YES | NO | 1 |  | 20 | [9 empty] | 5 | 2020-02-28 | 2020-03-03 | 2020-03-04 |  | Shipped | 7948
19071 | Ascent Gulch | MS-1 | E Lizardi | NO | NO | 11 | 4 | 2 | 7 | [8 empty] | 4 | 2020-02-26 | 2020-03-09 |  |  | Shipped | 7948
[6 empty] | 21 | 634 | 26 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144
2020-03-09
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1873 | Reston Office Bldg 3 | PAP-3A | K Burgess | NO | NO | 17 | [6 empty] | 22 |  |  |  |  | 12 | 2020-02-20 | 2020-03-16 |  |  | Shipped | 7948
1873 | Reston Office Bldg 3 | PAP-9 | K Burgess | YES | NO | 5 | [6 empty] | 28 |  |  |  |  | 121 | 2020-02-18 | 2020-03-16 |  |  | Shipped | 7948
1873 | Reston Office Bldg 3 | PAP-10 | K Burgess | NO | NO | 30 | [6 empty] | 30 |  |  |  |  | 165 | 2020-02-18 | 2020-03-16 |  |  | Shipped | 7948
1873 | Reston Office Bldg 3 | PAP-14A | K Burgess | NO | NO | 20 | [6 empty] | 20 |  |  |  |  | 110 | 2020-02-20 | 2020-03-16 | 2020-02-27 |  | Shipped | 7948 | Sheets were sent to 7948 for backrouting 2/27
1873 | Reston Office Bldg 3 | PAP-14 | K Burgess | YES | NO | [7 empty] | 165 |  |  |  |  | 908 | 2020-02-18 | 2020-03-16 | 2020-03-17 |  | Shipped | 7948 | Priority list was given yesterday per PM working ongetting panels 68-81 cut and ready to ship to site by early next week.
19090 | SCAD Victory Drive Student Housing | MS-MU1 | L Bonilla | NO | NO | 1 |  | 1 | [9 empty] | 1 | 2020-03-04 | 2020-03-11 |  |  | Shipped | 7948
19036 | Phipps Plaza Anchor | MS-2 | M Persons | NO | NO | 4 | 10 | 3 | [9 empty] | 3 | 2020-03-06 | 2020-03-10 | 2020-03-10 |  | Shipped | Site
19037 | Phipps Plaza Hotel | MS-1 | M Persons | NO | NO | 6 | 5 | 8 | [9 empty] | 3 | 2020-03-06 | 2020-03-10 | 2020-03-10 |  | Shipped | Site
[6 empty] | 241 | 4012 | 690 | 1 | 0 | 0 | 0 | 387 | 0 | 0 | 0 | 2 | 2923
2020-03-16
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1744 | Ripley East | PAP-4 | G Espinell | NO | 3535 | 6 | [6 empty] | 7 |  |  |  |  | 32 | 2020-02-10 | 2020-02-24 | 2020-03-18 |  | Shipped | FD
1771 | MD Project | MS-20 | M Kunz | NO | NO | 7 | 122 | [10 empty] | 15 | 2020-03-13 |  | 2020-03-19 |  | Shipped | 7948
1833 | University of Maryland | MS-7 | J Howard | NO | NO | 1 | [8 empty] | 30 |  |  | 1 | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | Shipped | Site
1859 | MCCNO Linear Park | MS-15 | M Jacobson | NO | NO | 2 |  | 57 | [9 empty] | 14 | 2020-03-11 | 2020-03-16 | 2020-03-16 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | MS-12 | K Burgess | NO | 3501 | 1 | 32 | [10 empty] | 4 | 2020-03-10 | 2020-03-16 | 2020-03-17 |  | Shipped | FD | Kyle has been advised that the on-site date is not possible due to the paint required. Wewill have it ready to ship to FD by the end of the week.
1873 | Reston Office Bldg 3 | MS-13 | K Burgess | NO | NO | 1 |  | 35 | [9 empty] | 9 | 2020-03-10 | 2020-03-16 | 2020-03-16 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | MS-14 | K Burgess | NO | 3596 | 3 |  | 11 | [9 empty] | 3 | 2020-03-18 | 2020-03-18 | 2020-03-20 |  | Shipped | FD
1873 | Reston Office Bldg 3 | MS-15 | K Burgess | NO | NO | 3 |  | 15 | [9 empty] | 4 | 2020-03-18 | 2020-03-18 | 2020-03-19 |  | Shipped | Site | Waiting on Material info. From Kyle
1883 | 1050 17th Street | MS-6 | S Hadley | NO | NO | 3 |  | 19 | [9 empty] | 5 | 2020-03-09 | 2020-03-21 |  |  | Shipped | Site
1883 | 1050 17th Street | MS-7 | S Hadley | NO | NO | 2 | 85 | [7 empty] | 135 |  |  | 12 | 2020-03-13 | 2020-03-17 | 2020-03-16 |  | Shipped | Site
1883 | 1050 17th Street | MS-8 | S Hadley | NO | NO | 1 |  | 1 | [9 empty] | 1 | 2020-03-16 | 2020-03-17 | 2020-03-16 |  | Shipped | Site
1883 | 1050 17th Street | PAP-4 | S Hadley | NO | NO | 2 | 10 | 10 |  |  |  |  | 20 |  |  |  |  | 12 | 2020-03-13 | 2020-03-21 | 2020-03-19 |  | Shipped | 7948
1883 | 1050 17th Street | PAP-1 | S Hadley | NO | NO | 1 |  | 28 | [9 empty] | 7 | 2020-03-20 | 2020-03-28 |  |  | Shipped | Site
1883 | 1050 17th Street | MS-9 | S Hadley | NO | NO | 3 |  | 14 | [9 empty] | 3 | 2020-03-19 | 2020-03-20 |  |  | Shipped | Site
19005 | MTAPD District 9 Police | MS-01 | M Jacobson | NO | NO | 1 | 36 | [10 empty] | 5 | 2020-03-06 |  | 2020-03-27 |  | Shipped | Site
19006 | Georgia Aquarium 2020 Exp | MS-11 | S Orrell | NO | NO | 4 |  | 41 | [9 empty] | 11 | 2020-03-09 | 2020-03-17 | 2020-03-17 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-10 | S Orrell | YES | NO | 2 | 800 | [10 empty] | 100 | 2020-03-02 | 2020-03-09 |  |  | Shipped | Site
19012 | Hyatt PL Perimeter Mall | MS-4 | J Howard | NO | NO | 1 | 1 | 45 | [9 empty] | 12 | 2020-03-17 | 2020-03-18 | 2020-03-19 |  | Shipped | Site
19012 | Hyatt PL Perimeter Mall | MS-5 | J Howard | NO | NO | 5 | 84 | 81 | [9 empty] | 6 |  |  | 2020-03-19 |  | Shipped | Site | Will be complete 3//19
19012 | Hyatt PL Perimeter Mall | MS-6 | J Howard | NO | NO | 1 |  | 16 | [9 empty] | 2 | 2020-03-19 | 2020-03-24 | 2020-03-19 |  | Shipped | Site
19047 | Project Charisma | MS-PL | C Jaunsen | NO | NO | 1 |  | 4 | [9 empty] | 1 | 2020-03-18 | 2020-03-19 |  |  | Shipped | 7948
19090 | SCAD Victory Drive Student Housing | MMU-1 REV | S Orell | NO | NO | 1 |  | 2 | [9 empty] | 1 | 2020-03-17 | 2020-03-19 | 2020-03-19 |  | Shipped | 7948 | Will be complete 3/18
[6 empty] | 52 | 1170 | 379 | 0 | 0 | 0 | 0 | 27 | 0 | 165 | 0 | 0 | 260
2020-03-23
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1550 | New Office Bldg F | MS-31 repair | T Messer | NO | NO | 1 |  | 2 | [9 empty] | 1 | 2020-03-10 |  |  |  | Shipped |  | Waiting to be painted
1838 | Fairfield Area Library | MS-PL1 | C Jaunsen | NO | NO | 2 |  | 6 | [9 empty] | 2 | 2020-03-26 | 2020-03-28 | 2020-04-14 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | LVR-1,2 | K Burgess | NO | NO | 11 |  | 352 | [9 empty] | 88 | 2020-02-25 | 2020-03-11 |  |  | Shipped | Site | All blades that were ready and clip assemblies with the exception of the 21 of the 6" galvanized assemblies shipped 3/14 balance of galvanized assemblies and additional angles required shipped to site. All blades are cut the balance yet to be delivered is now at F.D awaiting paint. 3/23
1883 | 1050 17th Street | PAP-1R | S Hadley | NO | 3426 | 119 | [6 empty] | 119 |  |  |  |  | 952 | 2020-02-14 | 2020-02-26 | 2020-03-12 |  | Shipped | Site | 2 perf panels to be punched all others have been completed in the Metalshop
1883 | 1050 17th Street | PAP-6 | S Hadley | NO | NO | 5 | [6 empty] | 3 |  |  |  |  | 27 | 2020-03-09 | 2020-03-21 |  |  | Shipped | Site
1883 | 1050 17th Street | MS-2R | S Hadley | NO | NO | 1 |  |  | 1 | [8 empty] | 1 | 2020-02-11 | 2020-03-10 |  |  | Shipped | Site
1883 | 1050 17th Street | MS-6 | S Hadley | NO | NO | 3 |  | 19 | [9 empty] | 3 | 2020-03-09 | 2020-03-21 |  |  | Shipped | Site | 2 releases same number one is Sample squares
19006 | Georgia Aquarium 2020 Exp | MS-13 | S Orrell | NO | NO | 1 | 20 | [10 empty] | 5 | 2020-03-26 | 2020-03-27 | 2020-03-27 |  | Shipped | 7948
19009 | W Nashville | MS-01 | T Gilstrap | NO | NO | 4 | 500 | 60 | [6 empty] | 30 |  |  | 80 | 2020-03-13 | 2020-04-01 |  |  | Shipped | 7948
19071 | Ascent Gulch | MS-01A | E Lizardi | NO | NO | 2 |  | 20 | [9 empty] | 5 | 2020-03-20 | 2020-04-06 |  |  | Shipped | 7948
[6 empty] | 149 | 520 | 459 | 1 | 0 | 0 | 0 | 122 | 0 | 30 | 0 | 0 | 1164
2020-03-30
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1891 | 1781 Peachtree | MS-2 | T Perry | NO | NO | 2 | 425 | [10 empty] | 53 | 2020-03-31 | 2020-04-15 | 2020-04-14 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-PSS01 | G Espinell | NO | NO | 7 | 220 | 176 | [8 empty] | 60 | 150 | 2020-02-27 | 2020-03-16 | 2020-03-17 |  | Shipped | Site | Waiting on material/ Arrived on 3/10 Waiting on additional instrustion from PM regarding MC-01 and MC-02 Required corners are being cut now (3/24)
1898 | Avalon 10000 | MS-18 | J Johns | NO | NO | 3 |  | 6 | [9 empty] | 2 | 2020-03-25 | 2020-03-26 | 2020-03-26 |  | Shipped | Site
18104 | Garco Mill Entertainment | MS-2B | C Jaunsen | YES | NO | 1 | 45 | [10 empty] | 6 | 2020-01-15 | 2020-01-22 |  |  | Delayed |  | On hold waiting on material, Should arrive by 3/6 Stil on hold until PM chooses Material
18104 | Garco Mill Entertainment | MS-6 | C Jaunsen | NO | NO | 1 |  | 18 | [9 empty] | 5 | 2020-03-27 | 2020-04-02 | 2020-04-01 |  | Shipped | Site
18105 | Potomac Shore MS | MS-01 | T Harwell | NO | NO | 4 | 545 | 6 | [9 empty] | 68 | 2020-03-27 | 2020-04-07 |  |  | Shipped | Site
19006 | Georgia Aquarium 2020 Exp | MS-12 | S Orrell | NO | NO | 9 | 630 | 126 | [9 empty] | 110 | 2020-03-25 | 2020-04-08 |  |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-14 | S Orrell | NO | NO | 2 |  | 36 | [9 empty] | 9 | 2020-03-27 | 2020-03-20 | 2020-03-31 |  | Shipped | 7948
19009 | W Nashville | MS-02 | C. Tucker | NO | NO | 4 | 500 | 85 |  | 50 |  |  |  |  | 500 |  |  | 92 | 2020-03-18 | 2020-04-01 |  |  | Shipped | 7948
19022 | UAB McCallum Phase I | MS-01 | N Dowd | NO | NO | 6 | 2900 | 96 | [9 empty] | 365 | 2020-02-25 | 2020-03-14 | 2020-03-13 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-MUFR2 |  | NO | NO | 1 | [10 empty] | 2 | 24 |  |  |  |  | Shipped | 7948 | Awaiting additional material.
19074 | VT Student Athletic Performance Center | MS-01 | M Jacobson | NO | NO | 4 | 88 | [10 empty] | 11 | 2020-03-27 | 2020-04-01 |  |  | Shipped | 7948
19084 | Fulton County South STEM School | MS-00 | C Whitehorne | NO | NO | 2 | 1 | 1 | [9 empty] | 1 | 2020-03-26 | 2020-04-06 | 2020-04-14 |  | Shipped | 7948
[6 empty] | 46 | 5354 | 550 | 0 | 50 | 0 | 0 | 0 | 0 | 500 | 0 | 62 | 896
2020-04-06
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1874 | Twelve24 | MS-Valet 1 | M Walker | NO | NO | 4 |  | 25 | [9 empty] | 6 | 2020-04-07 | 2020-04-21 | 2020-04-14 |  | Shipped | 7948
1883 | 1050 17th Street | MS-10 | S Hadley | NO | NO | 1 |  | 5 | [9 empty] | 2 | 2020-03-30 | 2020-04-03 | 2020-04-14 |  | Shipped | 7948
1883 | 1050 17th Street | MS-12 | S Hadley | NO | NO | 2 | 18 | [10 empty] | 2 | 2020-04-03 | 2020-04-07 | 2020-04-14 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-01 | G Espinell | YES | NO | 13 | 564 | 54 | [9 empty] | 84 | 2020-03-30 | 2020-04-13 | 2020-04-08 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-2A | G Espinell | YES | NO | 5 | 96 | 32 | [9 empty] | 20 | 2020-03-30 | 2020-04-13 | 2020-04-08 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-3A | G Espinell | YES | NO | 3 | 8 | 23 | [6 empty] | 48 |  |  | 10 | 2020-03-30 | 2020-04-13 | 2020-04-08 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-4A | G Espinell | YES | NO | 4 | 48 | 24 | [9 empty] | 12 | 2020-03-30 | 2020-04-13 | 2020-04-08 |  | Shipped | 7948
18104 | Garco Mill Entertainment | MS-07 | C Jaunsen | NO | NO | 2 | 18 | [10 empty] | 2 | 2020-03-31 | 2020-04-08 | 2020-04-14 |  | Shipped | 7948
18108 | UAB Residence Hall 2020 | MS-01 | B Grizzard | NO | NO | 4 | 185 | 24 | [9 empty] | 30 | 2020-03-31 | 2020-04-15 | 2020-04-14 |  | Shipped | 7948
19042 | 1300 4th Street NE | MS-04 | C Whitehorne | NO | 3594 | 6 | 90 | 41 | [9 empty] | 22 | 2020-03-24 | 2020-04-27 | 2020-04-14 |  | Shipped | 7948 | Galv. Is ready for pick up all other items shipped to FD on 4/8
[6 empty] | 44 | 1027 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 190
2020-04-13
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1771 | MD Project | MS-21 REV | M Kunz | NO | NO | 8 | 63 | 50 | [9 empty] | 20 | 2020-03-30 | 2020-04-10 | 2020-04-17 |  | Shipped | Site | Waiting to hear direction from PM regarding 6/265 &3/265T rest of release is complete.Working on last part 4.15
1786 | 45 L Street | PAP-1R | E Lizardi | NO | 3595 | 3 | [6 empty] | 1 | [5 empty] | 2020-04-07 | 2020-04-09 | 2020-04-16 |  | Shipped | FD
1871 | Element Southpark | MS-04 | G Espinell | YES | 3361 | 5 |  | 11 | [9 empty] | 4 | 2020-04-01 | 5/`2 | 2020-04-16 |  | Shipped | FD
1871 | Element Southpark | MS-2A | G Espinell | YES | NO | 7 |  | 9 | 47 | [5 empty] | 5 |  |  | 15 |  |  | 2020-04-14 |  | Shipped | 7948
1883 | 1050 17th Street | MS-11 | S.Hadley | NO | NO | 3 |  |  | 5 | [9 empty] | 2020-04-08 |  | 2020-04-14 |  | Shipped | 7948
1883 | 1050 17th Street | MS-6 | S Hadley | NO | NO | 3 |  | 19 | [9 empty] | 3 | 2020-03-09 | 2020-03-21 |  |  | Shipped | Site | 2 releases same number one is Sample squares
18107 | Felsenthal Residence | MS-02 | C Whitehorne | NO | NO | 5 |  | 96 | [9 empty] | 24 | 2020-04-03 | 2020-04-24 | 2020-04-14 |  | Shipped | 7948
18111 | BHSF Plantation MOB | MS-04 | B Grizzard | NO | NO | 1 |  | 8 | [9 empty] | 2 | 2020-04-09 | 2020-06-01 | 2020-04-14 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-5REV | S. Orell | YES | NO | 2 |  | 5 |  | 6 | [7 empty] | 4 | 2020-04-10 | 2020-04-14 | 2020-04-14 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-12REV | S Orrell | NO | NO | 1 | 200 | [10 empty] | 25 | 2020-04-14 | 2020-04-15 | 2020-04-15 |  | Shipped | Site
19016 | Rush Univ Medical Ctr NAB | MS-02 | M Jacobson | NO | NO | 1 | 3 | [10 empty] | 1 | 2020-04-07 | 2020-04-27 | 2020-04-14 |  | Shipped | 7948
19085 | Bellyard at the Interlock | MS-MU2 | N Dowd | NO | NO | 1 | 2 | 1 | [10 empty] | 2020-04-09 | 2020-04-15 | 2020-05-01 |  | Shipped | 7948
19072 | Oak Grove R&G | MS-01 | C Whitehorne | NO | NO | 4 | 154 | 187 | [9 empty] | 66 | 2020-04-03 | 2020-05-04 | 2020-04-14 |  | Shipped | 7948
[6 empty] | 44 | 422 | 386 | 52 | 6 | 0 | 0 | 1 | 0 | 5 | 0 | 0 | 164
April 20,2020
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1838 | Fairfield Area Library | MS-PL-2 | C Jaunsen | YES | NO | 4 | 24 | [10 empty] | 3 | 2020-04-17 | 2020-04-22 | 2020-06-01 |  | Shipped | 7948
1859 | MCCNO Linear Park | MS-16 | M Jacobson | NO | NO | 2 | [8 empty] | 300 |  |  | 15 | 2020-04-23 | 2020-04-27 | 2020-04-29 |  | Shipped | 7948
1874 | Twelve24 | MS-PS-1 | T Messer | NO | NO | 2 |  | 35 | [9 empty] | 9 | 2020-04-22 | 2020-05-05 | 2020-04-28 |  | Shipped | Site
18105 | Potomac Shore MS | MS-2 | T Harwell | NO | NO | 7 | 1460 | 86 | [9 empty] | 204 | 2020-04-08 | 2020-04-20 | 2020-04-21 |  | Shipped | 7948 | actual release date was 4/14
18107 | Felsenthal Residence | MS-03 | C Whitehorne | NO | NO | 2 | 18 | 4 | [9 empty] | 3 | 2020-04-24 | 2020-05-04 | 2020-05-01 |  | Shipped | 7948
19042 | 1300 4th Street NE | MS-05 | C Whitehorne | NO | NO | 5 | 196 |  | 14 | [6 empty] | 220 |  | 50 | 2020-03-26 | 2020-04-06 | 2020-04-09 |  | Shipped | 7948
19072 | Oak Grove R&G | MS-02 | C Whitehorne | YES | NO | 3 |  | 126 | [9 empty] | 32 | 2020-04-16 | 2020-05-04 | 2020-05-01 |  | Shipped | 7948
[6 empty] | 25 | 1698 | 251 | 14 | 0 | 0 | 0 | 0 | 0 | 300 | 220 | 0 | 316
2020-04-27
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1891 | 1781 Peachtree | MS-3 | P Reynolds | YES | NO | 2 | 91 | [10 empty] | 11 | 2020-04-24 | 2020-05-11 | 2020-05-01 |  | Shipped | 7948
1896 | North Hills Tower IV | PAP-1A | G Espinell | YES | 3035 | 13 | [6 empty] | 18 |  |  |  | 74 | 90 | 2020-04-08 | 2020-04-22 | 2020-05-21 |  | Shipped | Site | End caps are ready for pick up shipped to FD 5/1
1896 | North Hills Tower IV | PAP-1B | G Espinell | YES | 3031 | 31 | 140 | 24 |  |  |  |  | 26 |  |  |  | 28 | 130 | 2020-04-08 | 2020-04-22 | 2020-05-21 |  | Shipped | Site | Partial pickup 4/14 still working on the Panels Shipped to FD 5/1
19010 | Star Metals Office | MS-1 | S. Hardley | NO | NO | 4 | 111 | [10 empty] | 12 | 2020-04-13 | 2020-04-27 | 2020-04-30 |  | Shipped | 7948
19022 | UAB McCallum Phase I | MS-2 | N Dowd | NO | NO | 7 |  | 70 | [7 empty] | 500 |  | 25 | 2020-04-06 | 2020-05-02 | 2020-05-01 |  | Shipped | 7948
19042 | 1300 4th Street NE | PAP-4 | C Whitehorne | YES | 3593 | 89 | [6 empty] | 103 |  |  |  |  | 720 | 2020-03-24 | 2020-04-27 | 2020-04-30 |  | Shipped | FD
19061 | Rosslyn City Center | MS-2 | M Jacobson | NO | NO | 27 | [11 empty] | 4 | 2020-04-27 | 2020-04-28 | 2020-04-29 |  | Shipped | other see remarks | Shipped to Southern Alum. For anodizing
[6 empty] | 173 | 342 | 94 | 0 | 0 | 0 | 0 | 147 | 0 | 0 | 500 | 102 | 992
2020-05-04
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1771 | MD Project | MS-22 | M Kunz | NO | NO | 1 | 330 | [10 empty] | 130 | 2020-04-30 | 2020-05-11 | 2020-05-13 |  | Shipped | 7948
1796 | 4040 Wilson Blvd | MS-26 | S Orrell | YES | NO | 2 |  | 24 | [9 empty] | 6 | 2020-04-28 | ASAP |  |  | Shipped | 7948
1811 | State Farm Park Center Phase II | MS-17B | M Walker | NO | NO | 10 | 74 | [10 empty] | 10 | 2020-05-01 | 2020-05-07 | 2020-05-12 |  | Shipped | 7948
1859 | MCCNO Linear Park | MS-17 | M Jacobson | NO | NO | 1 |  | 12 | [9 empty] | 3 | 2020-05-05 | 2020-05-11 | 2020-05-07 |  | Shipped | 7948 | Parts revised due to lack of material.
1871 | Element Southpark | MS-02A1 | G Espinell | NO | NO | 1 | 3 | [10 empty] | 1 | 2020-05-05 | 2020-05-18 | 2020-05-19 |  | Shipped | Site
1873 | Reston Office Bldg 3 | PAP-12 | K Burgess | NO | NO | 21 | [6 empty] | 21 |  |  |  |  | 147 | 2020-04-20 | 2020-04-27 | 2020-05-01 |  | Shipped | Site
1873 | Reston Office Bldg 3 | LVR-3 | K Burgess | NO | NO | 8 |  |  |  |  | 128 | [6 empty] | 42 | 2020-04-09 | 2020-04-15 | 2020-05-02 |  | Shipped | Site
1873 | Reston Office Bldg 3 | MS-18 | K Burgess | NO | 3664 | 1 |  | 6 | [9 empty] | 2 | 2020-04-29 | ASAP | 2020-05-05 |  | Shipped | FD
1873 | Reston Office Bldg 3 | MS-17 | K Burgess | NO | 3664 | 1 |  | 4 | [9 empty] | 1 | 2020-04-29 | ASAP | 2020-05-05 |  | Shipped | FD
1874 | Twelve24 | MS-VALET-01 | T Messer | NO | NO | 1 |  | 12 | [9 empty] | 6 | 2020-04-30 | 2020-05-05 | 2020-05-04 |  | Shipped | 7948
1883 | 1050 17th Street | PAP-1RM2 | S Hadley | NO | NO | 2 | [6 empty] | 2 |  |  |  |  | 14 | 2020-04-29 | ASAP | 2020-05-01 |  | Shipped | Site
1883 | 1050 17th Street | PAP-1RM3 | S Hadley | NO | NO | [7 empty] | 1 |  |  |  |  | 12 | 2020-05-05 | ASAP | 2020-05-07 |  | Shipped | 7948
1883 | 1050 17th Street | MS-10R | S Hadley | YES | NO | 1 |  | 1 | [9 empty] | 1 | 2020-05-07 | 2020-05-07 | 2020-05-06 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-16 | S Orell | YES | NO | 1 | 500 | [10 empty] | 66 | 2020-04-27 | 2020-04-28 | 2020-04-28 |  | Shipped | Site
19006 | Georgia Aquarium 2020 Exp | MS-12A | S Orell | NO | NO | 2 |  | 50 | [9 empty] | 13 | 2020-05-07 | 2020-05-08 | 2020-05-11 |  | Shipped | Site
19010 | Star Metals Office | MS-1R | S. Hardley | NO | NO | 1 | 27 | [10 empty] | 4 | 2020-05-04 | 2020-05-05 | 2020-05-05 |  | Shipped | Site
19045 | Rio STEAM K-8 Campus | MS-01 | S Wright | NO | NO | 0 | [10 empty] | 173 | 18 | 2020-05-01 | 2020-05-08 | 2020-05-06 |  | Shipped | 7948 | Short 5 sticks of Perf. We are waiting on material
19072 | Oak Grove R&G | MS-04 | C Whitehorne | YES | NO | 2 | 505 | [10 empty] | 48 | 2020-04-28 | 2020-05-20 | 2020-05-11 |  | Shipped | 7948
19072 | Oak Grove R&G | MS-3 | C Whitehorne | YES | NO | 2 | 1270 | [10 empty] | 158 | 2020-04-22 | 2020-05-11 | 2020-05-07 |  | Shipped | 7948
[6 empty] | 58 | 2709 | 109 | 0 | 0 | 128 | 0 | 24 | 0 | 0 | 0 | 173 | 682
2020-05-11
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1771 | MD Project | MS-23 | M Kunz | NO | NO | 15 | 251 | [10 empty] | 34 | 2020-05-06 | ASAP | 2020-05-13 |  | Shipped | 7948
1873 | Reston Office Bldg 3 | PAP-2B | K. Burgess | YES | NO | 23 | [6 empty] | 49 |  |  |  |  | 343 | 2020-04-21 | ASAP | 2020-05-13 |  | Shipped | 7948 | All parts have been punched 5/4
1873 | Reston Office Bldg 3 | PAP-11 | K Burgess | NO | NO | 5 | [6 empty] | 21 |  |  |  |  | 147 | 2020-04-29 | ASAP | 2020-05-13 |  | Shipped | 7948
1874 | Twelve24 | Valet-03 | T.Messer | NO | NO | 1 |  | 2 | [9 empty] | 3 | 2020-05-11 | 5,12 | 2020-05-12 |  | Shipped | Site | Delivered by M.Walker
1874 | Twelve24 | MS-SS-55 | T Messer | NO | NO | 1 |  | 1 | [9 empty] | 1 | 2020-05-15 | 2020-05-15 | 2020-05-15 |  | Shipped | Site | Delivered by M.Walker
18108 | UAB Residence Hall 2020 | MS-02 | B.Grizzard | YES | NO | 1 | 500 | [10 empty] | 30 | 2020-05-14 | 2020-05-18 | 2020-05-19 |  | Shipped | 7948
19009 | W Nashville | MS-3 FCP-05 | C Tucker | NO | NO | 5 | 200 |  |  | 30 | 30 | [6 empty] | 36 | 2020-05-11 | 2020-05-18 | 2020-05-19 |  | Shipped | 7948
19010 | Star Metals Office | MS-2 | S Hadley | YES | NO | 13 | 103 | 103 | [9 empty] | 39 | 2020-05-11 | 2020-05-25 | 2020-06-30 |  | Shipped | 7948
19012 | Hyatt PL Perimeter Mall | MS-08 | J Howard | NO | NO | 1 |  | 180 | [9 empty] | 14 | 2020-05-14 | 2020-05-15 | 2020-05-15 |  | Shipped | Site
19030 | 1105 West P'Tree Office | MS-Z01 | G Espinell | NO | NO | [11 empty] | 8 | 8 | 2020-05-05 | 2020-05-08 |  |  | Shipped | Site | released and withdrawn for revision in design
19030 | 1105 West P'Tree Office | MS-Z02 | G Espinell | YES | NO | 1 | 28 | [10 empty] | 4 | 2020-05-12 | 2020-06-01 | 2020-06-24 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-Z01R | G Espinell | YES | NO | 1 | 9 | [10 empty] | 2 | 2020-05-05 | 2020-05-08 | 2020-05-12 |  | Shipped | 7948
19061 | Rosslyn City Center | MS-03 | M Jacobson | NO | NO | 3 |  | 70 | [9 empty] | 18 | 2020-05-12 | 2020-05-18 | 2020-05-19 |  | Shipped | 7948
19077 | Sawmill Station Shopping Center | FCP-03 | N.Dowd | NO | NO | 4 | [9 empty] | 400 |  | 14 | 2020-05-11 | 2020-05-18 | 2020-05-27 |  | Shipped | 7948
19090 | SCAD Victory Drive Student Housing | MS-01 | S Orrell | NO | NO | 2 | 200 | 70 | [9 empty] | 44 | 2020-05-13 | 2020-06-05 | 2020-05-19 |  | Shipped | 7948
[6 empty] | 76 | 1291 | 426 | 0 | 30 | 30 | 0 | 70 | 0 | 0 | 400 | 8 | 737
2020-05-18
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1869 | Bank of the Ozarks HQ | MS-1 | T Perry | NO | NO | 2 |  | 35 | [9 empty] | 4 | 2020-05-19 | 2020-05-20 | 2020-05-20 |  | Shipped | Site
1871 | Element Southpark | MS-01A | G.Espinell | YES | NO | 2 |  | 26 | [9 empty] | 4 | 2020-04-01 | 2020-05-18 | 2020-05-18 |  | Shipped | 7948
1891 | 1781 Peachtree | MS-4 | P Reynolds | NO | NO |  |  | 8 | [9 empty] | 2 | 2020-05-19 | 2020-05-22 | 2020-05-20 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-03B | G Espinell | YES | NO | 5 | 126 | 8 | [9 empty] | 14 | 2020-05-14 | 2020-05-27 | 2020-05-21 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-04B | G Espinell | YES | NO | 3 | 54 | [10 empty] | 6 | 2020-05-14 | 2020-05-27 | 2020-05-21 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-02B | G Espinell | YES | NO | 4 | 100 | 26 |  | 25 | [7 empty] | 14 | 2020-05-14 | 2020-05-27 | 2020-05-19 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-18Rev | S Orrell | NO | NO | 2 |  | 45 | [9 empty] | 12 | 2020-05-19 | 2020-05-22 | 2020-05-21 |  | Shipped | Site
19012 | Hyatt PL Perimeter Mall | MS-07 | J Howard | NO | NO | 2 |  | 250 | [9 empty] | 63 | 2020-04-24 | 2020-04-29 | 2020-05-01 |  | Shipped | Site | Waiting on additional material
19012 | Hyatt PL Perimeter Mall | MS-08 | J Howard | NO | NO | 1 |  | 16 | [9 empty] | 3 | 2020-05-18 | 2020-04-29 | 2020-05-15 |  | Shipped | Site
19021 | The Works Parking Garage | MS-03 | C.Whitehorn | YES | NO | 2 | [6 empty] | 6 |  |  |  |  | 42 | 2020-05-14 | 2020-05-20 | 2020-05-22 |  | Shipped | Site
19021 | The Works Parking Garage | PAP-04R | C.Whitehorn | YES | NO | 2 | [6 empty] | 2 |  |  |  |  | 14 | 2020-05-11 | 2020-05-25 | 2020-05-22 |  | Shipped | Site
19030 | 1105 West P'Tree Office | MS-SPMU-01 | G.Espinell | NO | NO | 2 | [10 empty] | 2 | 12 | 2020-05-13 |  | 2020-05-20 |  | Shipped | 7948
19042 | 1300 4th Street NE | MS-06 | C.Whitehorn | YES | NO | 8 | 15 | 47 | 46 | 32 | [7 empty] | 22 | 2020-05-14 | 2020-05-20 | 2020-05-22 |  | Shipped | 7948 | Awaiting material recv. 5.18
19052 | Three Ballpark Center | MS-02 | E.Lizardi | NO | 3771 | 4 |  | 28 | [9 empty] | 12 | 2020-05-18 | ASAP | 2020-06-10 |  | Shipped
19052 | Three Ballpark Center | MS-03 | E.Lizardi | NO | 3771 | 4 |  | 33 | [9 empty] | 14 | 2020-05-18 | ASAP | 2020-06-10 |  | Shipped
19052 | Three Ballpark Center | MS-04 | E.Lizardi | NO | 3771 | 4 |  | 39 | [9 empty] | 15 | 2020-05-18 | ASAP | 2020-06-10 |  | Shipped
19072 | Oak Grove R&G | MS-01 LS-CF | C.Whitehorn | NO | NO | 4 |  | 40 |  | 64 | [7 empty] | 6 | 2020-05-18 | 2020-05-18 | 2020-01-18 |  | Shipped | 7948
19012 | Hyatt PL Perimeter Mall | MS-09 | J Howard | NO | NO | 5 | 290 | 210 | [9 empty] | 90 | 2020-05-21 | 2020-05-26 | 2020-05-28 |  | Shipped | 7948
1891 | 1781 Peachtree | MS-5 | P Reynolds | NO | NO | 1 |  | 1 | [9 empty] | 1 | 2020-05-22 | 2020-05-22 | 2020-05-22 |  | Shipped | Site
[6 empty] | 57 | 585 | 812 | 46 | 121 | 0 | 0 | 8 | 0 | 0 | 0 | 2 | 350
2020-05-25
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1871 | Element Southpark | MS-01A1 | G Espinell | NO | NO | 1 | [8 empty] | 32 |  |  | 1 | 2020-05-26 | 2020-05-26 | 2020-05-26 |  | Shipped | 7948
1811 | State Farm Park Center Phase II | MS-10 | J Howard | NO | NO | 1 | 1350 | [10 empty] | 168 | 2020-05-26 | 2020-05-30 | 2020-05-29 |  | Shipped | 7948 | Will have ready to ship by Friday 5/29
[6 empty] | 2 | 1618 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 5
2020-06-01
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1651 | The Bristol | MS-69 | J Howard | NO | NO | 1 |  | 5 | [9 empty] | 2 | 2020-06-03 | 2020-06-10 | 2020-06-30 |  | Shipped | 7948
1811 | State Farm Park Center Phase II | MS-20 | J Howard | NO | NO | 1 |  | 80 | [9 empty] | 20 | 2020-06-03 | 2020-06-08 | 2020-06-05 |  | Shipped | 7948
1833 | University of Maryland | MS-10 | J Howard | NO | NO | 9 |  | 87 | [9 empty] | 21 | 2020-06-03 | 2020-06-08 | 2020-06-05 |  | Shipped | 7948
18105 | Potomac Shore MS | MS-03 | B.Grizzard | NO | NO | 3 | 250 | 35 | [9 empty] | 40 | 2020-05-29 | 2020-06-03 | 2020-07-15 |  | Shipped | 7948
19042 | 1300 4th Street NE | MS-07 | C.Whitehorn | YES | NO | 2 | 27 | [10 empty] | 4 | 2020-06-05 | 2020-06-05 |  |  | Shipped | 7948
19073 | UM Student Rec Center | MS-1 | B.Grizzard | NO | NO | 1 |  | 50 | [9 empty] | 12 | 2020-05-29 | 2020-06-03 | 2020-06-26 |  | Shipped | 7948
20002 | TCCC Hangar | MS-1 | J Howard | NO | NO | 9 | 190 | 56 | [9 empty] | 37 | 2020-06-03 | 2020-06-08 | 2020-07-15 |  | Shipped | 7948 | waititing on material for 3 pieces changed to Silver Metallic
[6 empty] | 26 | 277 | 507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136
2020-06-08
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1811 | State Farm Park Center Phase II | MS-22 | J Howard | NO | NO | 5 |  | 639 | [9 empty] | 160 | 2020-06-08 | 2020-06-12 | 2020-06-19 |  | Shipped | Site | FL-4 & LS-4 WAS PICKED UP ON 6/9 SENT TO SITE
1833 | University of Maryland | MS-11 | J Howard | NO | NO | 1 | [10 empty] | 50 | 2 | 2020-06-08 | 2020-06-12 |  |  | Shipped | Site
19006 | Georgia Aquarium 2020 Exp | MS-19 | S Orrell | NO | NO | 2 |  | 43 | [9 empty] | 10 | 2020-06-08 | 2020-06-09 | 2020-06-09 |  | Shipped | Site
19009 | W Nashville | MS-05-FCP-07 | C Tucker | YES | NO | 4 | 300 | 60 | [9 empty] | 52 | 2020-06-08 | 2020-06-15 | 2020-06-23 |  | Shipped | 7948
19009 | W Nashville | MS-4 | C Tucker | NO | NO | 8 | 230 | 60 | [6 empty] | 30 |  |  | 50 | 2020-06-08 | 2020-06-15 | 2020-06-23 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-Z03 | G.Espinell | NO | NO | 2 | 64 | [10 empty] | 12 | 2020-06-08 | 2020-06-11 | 2020-06-09 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-01A | G Espinell | YES | 3820 | 3 | 24 | [11 empty] | 2020-06-09 | 2020-06-22 | 2020-06-25 |  | Shipped | FD
19079 | International African American Museum | MS-BAR | C Jaunsen | NO | YES | 1 |  |  | 7 | [9 empty] | 2020-06-08 | 2020-06-22 | 2020-07-15 |  | Shipped | 7948
19085 | Bellyard at the Interlock | MS-01 | N.Dowd | NO | NO | 6 | 208 | 200 | [9 empty] | 73 | 2020-06-03 | 2020-06-25 | 2020-06-30 |  | Shipped | 7948
1796 | 4040 Wilson Blvd | MS-26 REV | S Orrell | NO | NO | 2 |  | 40 | [9 empty] | 10 | 2020-06-10 | 2020-06-10 | 2020-06-26 |  | Shipped | 7948
[6 empty] | 34 | 826 | 1042 | 7 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 50 | 369
2020-06-15
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
19012 | Hyatt PL Perimeter Mall | MS-8 add-on | J Howard | NO | NO | 1 | 500 | [10 empty] | 63 | 2020-06-18 | 2020-06-19 | 2020-06-25 |  | Shipped | Site | p1 was deleivered to site on 6/18
19042 | 1300 4th Street NE | MS-08 | C Whitehorne | YES | NO | 14 | 567 | 163 | [9 empty] | 110 | 2020-06-12 | 2020-07-06 |  |  | Shipped | 7948
19009 | W Nashville | MS-6-MCM-1 | C Tucker | YES | NO | 8 | 135 | 140 | [6 empty] | 500 |  |  |  | 2020-06-17 | 2020-06-25 | 2020-06-23 |  | Shipped | 7948
18104 | Garco Mill Entertainment | MS-PL4 | C Jaunsen | NO | NO | 1 |  | 4 | [9 empty] | 1 | 2020-06-10 | 2020-06-15 |  |  | Shipped | 7948
19047 | Project Charisma | MS-PL2 | C Jaunsen | NO | NO | 2 |  | 9 | [9 empty] | 2 | 2020-06-12 | 2020-07-12 | 2020-06-30 |  | Shipped | 7948
19079 | International African American Museum | MS-A1 | C Jaunsen | NO | NO | 3 | 10 | [10 empty] | 2 | 2020-06-10 | 2020-06-18 | 2020-06-26 |  | Shipped | 7948
[6 empty] | 29 | 1212 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 178
2020-06-22
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1771 | MD Project | MS-24 | M Kunz | NO | NO | 1 | [10 empty] | 133 |  | 2020-06-23 | 2020-06-29 | 2020-06-30 |  | Shipped | 7948
1874 | Twelve24 | FL-02PLr1 | M Walker | NO | NO | 3 |  | 11 | [9 empty] | 3 | 2020-06-22 | 2020-06-23 | 2020-06-26 |  | Shipped | 7948
1874 | Twelve24 | Fl-01PLr1 | M Walker | NO | NO | 13 | 11 | 16 | [9 empty] | 6 | 2020-06-22 | 2020-06-23 | 2020-06-26 |  | Shipped | 7948
1874 | Twelve24 | FL-02PL-2 | M Walker | NO | NO | 1 |  | 2 | [9 empty] | 2 | 2020-06-22 | 2020-06-23 | 2020-06-26 |  | Shipped | 7948
1874 | Twelve24 | FL-03Pl | M Walker | NO | NO | 1 |  | 2 | [9 empty] | 1 | 2020-06-23 | 2020-06-24 | 2020-06-26 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-PAP-01C | G Espinell | NO | NO | 2 | [6 empty] | 36 | [5 empty] | 2020-06-11 | 2020-09-23 |  |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-PAP-01B | G Espinell | NO | NO | 2 | [6 empty] | 36 | [5 empty] | 2020-06-10 | 2020-09-23 |  |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-TA-01A | G Espinell | YES | NO | 1 | 72 | [10 empty] | 10 | 2020-06-15 | 2020-06-18 |  |  | Shipped | 7948 | Waiting on Material
19072 | Oak Grove R&G | MS-05 | C Whitehorne | NO | NO | 1 |  | 63 | [9 empty] | 9 | 2020-06-23 | 2020-07-20 | 2020-06-30 |  | Shipped | 7948
19090 | SCAD Victory Drive Student Housing | MS-2 | S Orrell | YES | NO | 4 |  | 64 | [9 empty] | 16 | 2020-06-23 | 2020-06-25 | 2020-06-30 |  | Shipped | 7948
20006 | The Adley at City Springs | MS-01 | P Reynolds | NO | NO | 1 | 3 | [10 empty] | 1 | 2020-06-22 | 2020-07-13 |  |  | Shipped | 7948
20002 | Coca-Cola Hangar | Call In | J Howard | NO | NO | 3 |  | 12 | [9 empty] | 3 | 2020-06-29 | 2020-06-30 | 2020-06-30 |  | Shipped | Site
[6 empty] | 33 | 86 | 170 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 133 | 51
2020-06-29
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1768 | The Charles | MS-102 | P Reynolds | YES | NO | 5 | 8 | 21 | [9 empty] | 6 | 2020-06-29 | 2020-07-06 |  |  | Shipped | Site
1873 | Reston Office Bldg 3 | MS-19 | K Burgess | NO | YES | 1 |  | 4 | [9 empty] | 1 | 2020-07-01 | 2020-07-01 | 2020-07-02 |  | Shipped | 7948
1896 | North Hills Tower IV | MS-PSS-02 | G Espinell | NO | NO | 4 | 18 | 8 | [9 empty] | 4 | 2020-05-12 | 2020-05-25 | 2020-07-02 |  | Shipped | 7948 | waiting on material PO 3693 ATAS Charcoal (Part# MC-02)partial pick sent to 7948 5/19
18104 | Garco Mill Entertainment | MS-Pl5 | C Jaunsen | NO | NO | 1 |  | 2 | [9 empty] | 1 | 2020-06-29 | 2020-07-08 |  |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-22 | S Orrell | NO | NO | 1 | 12 | [10 empty] | 2 | 2020-06-29 | 2020-07-01 | 2020-06-30 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-23 | S Orrell | NO | NO |  | 42 | [10 empty] | 11 | 2020-07-01 | 2020-07-06 | 2020-07-15 |  | Shipped | 7948
19010 | Star Metals Office | MS-03 | S Hadley | NO | NO | 4 |  | 18 | [6 empty] | 24 |  |  | 6 | 2020-06-23 | 2020-07-07 |  |  | Shipped | 7948 | (partial only the Flats stapping)
19010 | Star Metals Office | PSS-02 | S Hadley | YES | NO | 10 | 425 | 745 | [6 empty] | 400 |  |  | 243 | 2020-06-25 | 2020-08-03 | 2020-07-14 |  | Shipped | 7948
19010 | Star Metals Office | PSS-03 | S Hadley | YES | NO | 10 | 290 | 380 | [6 empty] | 200 |  |  | 134 | 2020-06-25 | 2020-08-24 | 2020-07-14 |  | Shipped | 7948
19010 | Star Metals Office | PSS-04 | S Hadley | YES | NO | 10 | 160 | 271 | [9 empty] | 88 | 2020-06-25 | 2020-08-24 | 2020-07-14 |  | Shipped | 7948
19022 | UAB McCallum Phase I | MS-4 | N Dowd | NO | NO | 2 | 800 | [8 empty] | 100 |  | 100 | 2020-07-01 | 2020-07-06 | 2020-07-06 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-PAP-1D | G Espinell | NO | NO | 2 | [6 empty] | 36 |  |  |  |  | 16 | 2020-06-11 | 2020-12-08 |  |  | Shipped | 7948
[6 empty] | 103 | 1755 | 1449 | 0 | 0 | 0 | 0 | 130 | 0 | 624 | 100 | 0 | 1270
2020-07-06
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1768 | The Charles | MS-103 | P Reynolds | NO | NI | 1 |  | 2 | [9 empty] | 1 | 2020-07-10 | 2020-07-10 |  |  | Shipped | 7948
1829 | The Living Building at Georgia Tech | MS-07 | G.Espinell | YES | NO | 1 | [10 empty] | 4 |  | 2020-07-06 | 2020-07-20 | 2020-07-15 |  | Shipped | 7948
1883 | 1050 17th Street | PAP-01XR | S.Hadley | NO | MO | 1 | [10 empty] | 1 |  | 2020-07-06 | 2020-07-06 | 2020-07-09 |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-18RP | S. Orrel | NO | NO | 2 |  | 10 | 15 | [9 empty] | 2020-07-06 | 2020-07-06 |  |  | Shipped | 7948
19006 | Georgia Aquarium 2020 Exp | MS-23 | S Orrell | NO | NO | 2 |  | 42 | [9 empty] | 10 | 2020-07-01 | 2020-07-06 | 2020-07-08 |  | Shipped | Site | remake angle changed
19030 | 1105 West P'Tree Office | MS-Z02B | G Espinell | NO | NO | 1 | 28 | [10 empty] | 4 | 2020-06-29 | 2020-07-06 |  |  | Shipped | Site
19030 | 1105 West P'Tree Office | MS-SSB | G.Espinell | NO | NO | 4 | [10 empty] | 18 | 24 | 2020-05-12 |  |  |  | Shipped |  | Tool Boxes per field crews request
19052 | Three Ballpark Center | MS-02B | E Lizardi | NO | NO | 4 |  | 28 | [9 empty] | 7 | 2020-07-07 | 2020-07-27 |  |  | Shipped
19052 | Three Ballpark Center | MS-02A | E Lizardi | No | NO | 1 | 20 | [10 empty] | 3 | 2020-06-22 | 2020-07-27 |  |  | Shipped
19061 | Rosslyn City Center | MS-04 | M Jacobson | NO | NO | 27 | 213 | 113 | [6 empty] | 50 |  |  | 58 | 2020-07-01 | 2020-07-13 | 2020-07-15 |  | Shipped | 7948
19072 | Oak Grove R&G | MS-07 | C Whitehorne | NO | NO | 1 | 176 |  |  | 80 | [7 empty] | 24 | 2020-07-02 | 2020-07-15 | 2020-07-15 |  | Shipped | 7948
19079 | International African American Museum | MS-BAR2 | C. Jaunsen | NO | NO | 1 |  |  | 8 | [9 empty] | 2020-07-03 | 2020-07-13 | 2020-07-09 |  | Shipped
19089 | Methodist Hospital | MS-1 | M Persons | NO | NO | 5 |  | 140 | [9 empty] | 35 | 2020-07-07 | 2020-07-09 |  |  | Shipped
19091 | TQL | MS-01-MCM-01 | C. Tucker | YES | NO | 3 | 300 | 20 |  | 20 |  |  |  |  | 500 |  |  |  | 2020-07-06 | 2020-07-13 | 2020-07-10 |  | Shipped | 7948
[6 empty] | 65 | 1471 | 442 | 23 | 100 | 0 | 0 | 0 | 0 | 550 | 0 | 23 | 274
2020-07-13
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1768 | The Charles | MS-104 | P Reynolds | YES | NO | 2 |  | 5 | [9 empty] | 1 | 2020-07-15 | 2020-07-17 | 2020-07-16 |  | Shipped | 7948
1871 | Element Southpark | MS-3 | G Espinell | YES | NO | 4 | 32 | 29 | [6 empty] | 32 |  |  | 11 | 2020-06-18 | 2020-07-06 | 2020-07-17 |  | Shipped | 7948
1871 | Element Southpark | MS-1B | G Espinell | YES | NO | 4 | 26 | 7 | [9 empty] | 8 | 2020-06-15 | 2020-06-29 | 2020-07-17 |  | Shipped | 7948
1871 | Element Southpark | MS-2B | G Espinell | YES | NO | 4 | 10 | 6 | [6 empty] | 10 |  |  | 4 | 2020-06-24 | 2020-07-07 | 2020-07-17 |  | Shipped | 7948
1871 | Element Southpark | MS-2C | G Espinell | YES | NO | 3 | 5 | [7 empty] | 10 |  |  | 2 | 2020-07-01 | 2020-07-20 | 2020-07-17 |  | Shipped | 7948
18105 | Potomac Shore MS | MS-4 | B Grizzard | NO | NO | 4 | 150 | 40 | [9 empty] | 23 | 2020-07-10 | 2020-07-15 | 2020-07-15 |  | Shipped | 7948
18111 | BHSF Plantation MOB | MS-05 | B Grizzard | NO | 3700 | 1 |  | 8 | [9 empty] | 2 | 2020-07-08 | 2020-07-27 | 2020-07-29 |  | Shipped | FD
19010 | Star Metals Office | MS-CB1 | S Hadley | NO | NO | 4 | 6 | 64 | [9 empty] | 17 | 2020-07-10 | 2020-07-14 | 2020-07-15 |  | Shipped | 7948 | Material deliveried on 7/13
19012 | Hyatt PL Perimeter Mall | Call In | J.Howard | YES | NO | 1 | 50 | [10 empty] | 2 | 2020-07-13 | 2020-07-13 | 2020-07-13 |  | Shipped | Site
19012 | Hyatt PL Perimeter Mall | MS-16 | J.Howard | NO | NO | 2 |  | 24 |  | 10 | [7 empty] | 12 | 2020-07-13 | 2020-07-15 | 2020-07-14 |  | Shipped | Site
19022 | UAB McCallum Phase I | MS-3 | N Dowd | YES | NO | 4 | 530 | [10 empty] | 66 | 2020-07-09 | 2020-07-18 | 2020-07-16 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-SP01 | G.Espinell | NO | NO | 1 | [7 empty] | 68 |  |  |  | 256 | 2020-06-17 |  | 2020-07-15 |  | Shipped | 7948
19042 | 1300 4th Street NE | PAP-1 | C Whitehorne | YES | 3819 | 53 | [6 empty] | 94 |  |  |  |  | 658 | 2020-06-10 | 2020-07-06 | 2020-07-17 |  | Shipped | Site | back from F.D 7/15 stiffeners and recrating as of 7/15
19061 | Rosslyn City Center | MS-05 | M Jacobson | NO | NO | 3 |  | 8 | [9 empty] | 2 | 2020-07-10 | 2020-07-27 |  |  | Shipped | 7948
19064 | The Osprey | MS-01 | T Perry | NO | NO | 3 | 20 | 4 | [9 empty] | 4 | 2020-07-15 | 2020-08-05 |  |  | Shipped
19072 | Oak Grove R&G | MS-06 | C Whitehorne | YES | NO | 2 | [10 empty] | 510 | 84 | 2020-06-25 | 2020-07-15 | 2020-07-15 |  | Shipped | 7948
19075 | Excelsior Mill | MS-01 | J Bilbrey | NO | NO | 6 | 54 | 67 | [9 empty] | 24 | 2020-07-08 | 2020-07-27 |  |  | Ready for Pick Up
19085 | Bellyard at the Interlock | MS-02 | N Dowd | NO | NO | 3 | 30 | 24 | [9 empty] | 10 | 2020-07-15 | 2020-07-21 |  |  | Ready for Pick Up
20002 | Coca-Cola Hangar | MS-007 | J Howard | NO | NO | 3 | 14 | 4 | [9 empty] | 4 | 2020-07-14 | 2020-07-15 |  |  | Shipped | Site
20002 | Coca-Cola Hangar | MS-08 | J Howard | NO | NO | 1 | 2 | [10 empty] | 1 | 2020-07-14 | 2020-07-15 | 2020-07-14 |  | Shipped | Site | Jason picked up
20002 | Coca-Cola Hangar | MS-08 | J Howard | NO | NO | 1 |  | 10 | [9 empty] | 2 | 2020-07-15 | 2020-07-15 | 2020-07-15 |  | Shipped | 7948
[6 empty] | 35 | 401 | 316 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 304
2020-07-20
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
19012 | Hyatt PL Perimeter Mall | MS-17 | J Howard | NO | NO | 2 |  | 3 | [9 empty] | 1 | 2020-07-16 | 2020-07-20 | 2020-07-20 |  | Shipped | 7948
19030 | 1105 West P'Tree Office | MS-FR1 | G Espinell | NO | NO | 7 | [7 empty] | 118 |  |  |  | 1180 | 2020-05-05 | 2020-06-01 |  |  | Ready for Pick Up |  | 6 frames remaining to be built 7/15
19030 | 1105 West P'Tree Office | MS-SP-02 | G Espinell | NO | NO | 2 | [10 empty] | 16 |  | 2020-07-07 | 2020-07-14 |  |  | Ready for Pick Up
19030 | 1105 West P'Tree Office | MS-SP-03 | G Espinell | NO | NO | 1 | [7 empty] | 4 |  |  |  |  | 2020-07-15 |  |  |  | Ready for Pick Up
19042 | 1300 4th Street NE | PAP-2A | C Whitehorne | NO | 3842 | 6 | [6 empty] | 8 |  |  |  |  | 56 | 2020-06-10 | 2020-07-13 | 2020-07-21 |  | Shipped | FD | additional paint ordered 7/13
19042 | 1300 4th Street NE | PAP-4A | C Whitehorne | No | YES | 18 | [6 empty] | 18 |  |  |  |  | 126 | 2020-06-23 | 2020-07-20 | 2020-07-21 |  | Shipped | FD | additional paint ordered 7/13
19042 | 1300 4th Street NE | PAP-2 | C Whitehorne | NO | 3822 | 6 | [6 empty] | 6 |  |  |  |  | 48 | 2020-06-10 | 2020-07-13 |  |  | Shipped | FD | additional paint ordered 7/13
19064 | The Osprey | MS-02 | T Perry | NO | NO | 4 |  | 33 | [9 empty] | 8 | 2020-07-17 | 2020-08-05 |  |  | Shipped
19089 | Methodist Hospital | MS-2 | M Persons | NO | NO | 4 |  | 43 | [9 empty] | 10 | 2020-07-16 | 2020-07-21 |  |  | Ready for Pick Up
19091 | TQL | MS-2-MCM-2 | C Tucker | YES | NO | 3 | 401 | 240 | [9 empty] | 112 | 2020-07-15 | 2020-07-22 | 2020-07-27 |  | Shipped | 7948
1771 | MD Project | MS-25 | M Kunz | NO | NO | 1 |  | 20 | [9 empty] | 5 | 2020-07-20 | 2020-07-24 | 2020-07-27 |  | Shipped | 7948
19064 | The Osprey | MS-3 | T Perry | YES | NO | 4 | 1 | 37 | [9 empty] | 10 | 2020-07-21 | 2020-08-05 |  |  | Shipped
1840 | Andrews Avenue Bridge Rehab | MS-1 | M Persons | NO | NO | 1 | 30 | [10 empty] | 4 | 2020-07-22 | 2020-07-27 |  |  | Ready for Pick Up
19009 | W Nashville | MS-08-PAP-MU | C Tucker | NO | NO | 8 | 10 | 30 |  |  |  |  | 5 | [5 empty] | 2020-07-21 | 2020-07-24 |  |  | Ready for Pick Up |  | Corten portion will be ready post move
1873 | Reston Office Bldg 3 | MS-20 | N Dowd | NO | NO | 2 |  | 16 | [9 empty] | 4 | 2020-07-24 | 2020-07-27 | 2020-07-27 |  | Shipped
1891 | 1781 Peachtree | MS-2 RMK | T Perry | NO | NO | 1 | 125 | [11 empty] | 2020-07-22 | 2020-07-23 |  |  | Ready for Pick Up
19089 | Methodist Hospital | MS-3 | M Persons | NO | NO | 1 |  | 9 | [9 empty] | 2 | 2020-07-23 | 2020-07-27 |  |  | Ready for Pick Up
[6 empty] | 81 | 807 | 471 | 15 | 0 | 0 | 0 | 37 | 122 | 0 | 0 | 16 | 1612
2020-07-27
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1883 | 1050 17th Street | PAP-64R | S Hadley | NO | NO | 1 | [6 empty] | 1 |  |  |  |  | 5 | 2020-07-17 | 2020-07-17 |  |  | Shipped
19042 | 1300 4th Street NE | PAP-4R | C Whitehorne | NO | YES | 2 | [6 empty] | 2 | [5 empty] | 2020-06-25 | 2020-07-20 |  |  | Ready for Pick Up | FD
19042 | 1300 4th Street NE | MS-6 | C Whitehorne | YES | NO | 2 | 510 | [10 empty] | 68 | 2020-06-25 | 2020-07-15 |  |  | Ready for Pick Up | FD
19052 | Three Ballpark Center | MS-3A | E Lizardi | NO | NO | 8 | 160 | 13 | 15 | [8 empty] | 30 | 2020-07-23 | 2020-08-21 |  |  | Ready for Pick Up
19012 | Hyatt PL Perimeter Mall | MS-15 | J Howard | NO | NO | 2 | 80 | 27 | [9 empty] | 16 | 2020-07-24 | 2020-07-26 | 2020-07-28 |  | Shipped
[6 empty] | 15 | 750 | 40 | 15 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 119
2020-08-03
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
19090 | SCAD Victory Drive Student Housing | MS-3 | S Orrell | NO | NO | 2 |  | 175 | [9 empty] | 44 | 2020-07-26 | 2020-07-30 | 2020-08-03 |  | Shipped | Site | 2020-08-06
19091 | TQL | MS-3-PSS | C Tucker | YES | NO | 17 |  | 157 |  | 157 | [7 empty] | 79 | 2020-07-22 | 2020-07-27 |  |  | Ready for Pick Up |  | 2020-08-06
19010 | Star Metals Office | MS-BG1 | S Hadley | YES | NO | 4 | 150 | 64 | [9 empty] | 35 | 2020-07-29 | ASAP |  |  | Ready for Pick Up |  | 2020-08-08
19090 | SCAD Victory Drive Student Housing | MS-4 | S Orrell | NO | NO | 2 |  | 18 | [9 empty] | 5 | 2020-07-28 | 2020-08-04 | 2020-08-03 |  | Shipped | Site
1771 | MD Project | MS-26 | M Kunz | NO | NO | 1 | 300 | [10 empty] | 38 | 2020-07-23 | 2020-08-06 |  |  | Ready for Pick Up
1771 | MD Project | MS-27 | M Kunz | NO | NO | 1 | 7 | [10 empty] | 1 | 2020-07-23 | 2020-08-06 |  |  | Ready for Pick Up
1840 | Andrews Avenue Bridge Rehab | MS-2 | M Persons | NO | NO | 7 |  | 37 | [9 empty] | 12 | 2020-08-06 | 2020-08-11 |  |  | Ready for Pick Up
19006 | Georgia Aquarium 2020 Exp | MS-24 | S Orrell | NO | NO | 1 | 9 | [11 empty] | 2020-08-05 | 2020-08-05 |  |  | Ready for Pick Up
1873 | Reston Office Bldg 3 | PAP-16R | N Dowd | YES | NO | 4 | [6 empty] | 4 | [5 empty] | 2020-08-06 |  |  |  | Ready for Pick Up
19042 | 1300 4th Street NE | PAP-4A-RM | C Whitehorne | NO | YES | 1 | [6 empty] | 1 | [5 empty] | 2020-08-05 | 2020-08-25 |  |  | Ready for Pick Up
1896 | North Hills Tower IV | PAP-03 | G Espinell | NO | YES | 2 |  | 34 | [9 empty] | 6 | 2020-08-05 | */7 |  |  | Ready for Pick Up | FD
1891 | 1781 Peachtree | MS-6 | T Perry | NO | NO | 1 | 70 | [11 empty] | 2020-08-05 | 2020-08-12 |  |  | Ready for Pick Up
1873 | Reston Office Bldg 3 | PAP-10RM | N Dowd | NO | NO | 14 | [6 empty] | 14 | [5 empty] | 2020-08-05 | ASAP |  |  | Ready for Pick Up
19009 | W Nashville | MS-9-FCP-2 | C Tucker | NO | NO | 2 |  | 20 | [10 empty] | 2020-08-04 | 2020-08-07 |  |  | Ready for Pick Up
1871 | Element Southpark | MS-3B | G Espinell | NO | NO | 1 |  | 6 | [10 empty] | 2020-08-04 | 2020-08-17 |  |  | Ready for Pick Up
[6 empty] | 37 | 386 | 115 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 62
2020-08-10
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1873 | Reston Office Bldg 3 | PAP-16R | N Dowd | YES | NO | 4 | [6 empty] | 4 | [5 empty] | 2020-08-06 | ASAP |  |  | Shipped | Site | Timcalled in changing the Color of previosly fabricated panels to Med. Gray
19072 | Oak Grove R&G | MS-08 REV | C. Whitehorn | NO | NO | 2 |  | 33 | [6 empty] | 170 |  |  |  | 2020-08-11 | 2020-08-17 |  |  | Ready for Pick Up
1840 | Andrews Avenue Bridge Rehab | MS-3 | M.Persons | NO | NO | 1 | 80 | [11 empty] | 2020-08-10 | 2020-08-10 |  |  | Ready for Pick Up
19006 | Georgia Aquarium 2020 Exp | MS-1A | S.Orrell | NO | NO | 2 | 4 |  |  | 6 | [12 empty] | Ready for Pick Up
19030 | 1105 West P'Tree Office | MS-Z-04 | G.Espinell | NO | NO | 1 | 6 | [11 empty] | 2020-08-05 | 2020-08-12 |  |  | Shipped | Site
19052 | Three Ballpark Center | MS-05 | E Lizardi | YES | NO | 11 | 350 | 77 |  | 49 | [8 empty] | 2020-08-04 | 2020-09-01 | 2020-08-20 |  | Shipped
20015 |  | HPL-1 | [14 empty] | 2595 | [5 empty] | Ready for Pick Up
19089 | Methodist Hospital | MS-4 | M.Persons | NO | NO | 3 |  | 60 | [10 empty] | 2020-08-07 | 2020-08-11 |  |  | Ready for Pick Up
19074 | VT Student Athletic Performance Center | MS01 | M.Jacobson | NO | NO | 5 | 64 | [11 empty] | 2020-08-12 | 2020-09-08 |  |  | Ready for Pick Up
R10674 | [15 empty] | 1075 | [6 empty] | Ready for Pick Up
R10688 | [6 empty] | 8 | [9 empty] | 57 | [5 empty] | Ready for Pick Up
19022 | UAB McCallum Phase I | MS-05 | N.Dowd | NO | NO | 1 | [9 empty] | 100 |  |  | 2020-08-13 | 2020-08-17 | 2020-08-17 |  | Shipped
20036 | Everleigh Duluth | MS-MU-1 | S.Orrell | YES | NO | 12 | 8 | 8 | [10 empty] | 2020-08-10 |  |  |  | Ready for Pick Up
19009 | W Nashville | MS-7-FCP-8 | C Tucker | NO | NO | 5 | 200 | 40 | [10 empty] | 2020-08-13 | 2020-08-14 |  |  | Ready for Pick Up
[6 empty] | 47 | 720 | 218 | 0 | 55 | 0 | 0 | 4 | 0 | 170 | 1175 | 2652 | 0
2020-08-17
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
19030 | 1105 West P'Tree Office | MS-TA-01A | G Espinell | YES | NO | [11 empty] | 72 |  | 2020-07-31 | 2020-08-17 |  |  | In Progress
19085 | Bellyard at the Interlock | MS-3 | N Dowd | NO | NO | 9 | 70 | 75 | [7 empty] | 782 |  |  | 2020-08-06 | 2020-08-25 |  |  | Ready for Pick Up |  | additional material required/ all clips are ready for pick up 8/17
1871 | Element Southpark | MS-5A | G Espinell | NO | NO | 1 | 72 | [11 empty] | 2020-08-05 | 2020-08-24 |  |  | Ready for Pick Up |  | going in crate with mcm-5a
1811 | State Farm Park Center Phase II | MS-23 | J Howard | NO | NO | 2 |  | 35 | [9 empty] | 9 | 2020-08-17 | 2020-08-21 | 2020-08-20 |  | Shipped
20036 | Everleigh Duluth | MS-MU2 | L Bonilla | NO | NO | 3 | 3 | 10 | [9 empty] | 3 | 2020-08-17 | 2020-08-17 |  |  | Ready for Pick Up
19012 | Hyatt PL Perimeter Mall | MS-18 | J Howard | NO | NO | 3 | 8 | [10 empty] | 1 | 2020-08-17 | 2020-08-21 | 2020-08-21 |  | Shipped
19012 | Hyatt PL Perimeter Mall | MS-19 | J Howard | NO | NO | 3 |  | 24 | [9 empty] | 5 | 2020-08-17 | 2020-08-21 | 2020-08-21 |  | Shipped
19012 | Hyatt PL Perimeter Mall | MS-20 | J Howard | NO | NO | 3 |  | 24 | [9 empty] | 5 | 2020-08-17 | 2020-08-21 | 2020-08-21 |  | Shipped
19012 | Hyatt PL Perimeter Mall | MS-21 | J Howard | NO | NO | 1 |  | 5 | [9 empty] | 2 | 2020-08-17 | 2020-08-21 | 2020-08-21 |  | Shipped
19009 | W Nashville | MS-10-FCP-06 | C Tucker | NO | NO | 5 | 250 | 130 | [9 empty] | 65 | 2020-08-13 | 2020-08-18 |  |  | Ready for Pick Up
1871 | Element Southpark | MS-01A2 | G Espinell | NO | NO | 1 |  | 2 | [9 empty] | 1 | 2020-08-17 | 2020-08-21 |  |  | Ready for Pick Up
19091 | TQL | MS-4-MCM-4 |  | NO | NO | 2 |  | 145 | [9 empty] | 37 | 2020-08-17 | 2020-08-21 |  |  | Ready for Pick Up
19012 | Hyatt PL Perimeter Mall | MS-99 | J Howard | NO | NO | 2 |  | 20 | [9 empty] | 5 | 2020-08-19 | 2020-08-20 | 2020-08-20 |  | Shipped
19064 | The Osprey | MS-4 | T Perry | NO | NO | 1 | 1 | [10 empty] | 1 | 2020-08-19 | 2020-08-20 | 2020-08-20 |  | Shipped
1811 | State Farm Park Center Phase II | MS-97 | J Howard | NO | NO | 1 | 150 | [10 empty] | 19 | 2020-08-19 | 2020-08-21 |  |  | Ready for Pick Up
19010 | Star Metals Office | 3X | S Hadley | NO | NO | 2 |  | 4 | [9 empty] | 1 | 2020-08-19 | ASAP |  |  | Ready for Pick Up
19006 | Georgia Aquarium 2020 Exp | MS-30 | S Orrell | NO | NO | 2 | [10 empty] | 4 | 4 | 2020-08-19 | 2020-08-20 |  |  | Ready for Pick Up
19006 | Georgia Aquarium 2020 Exp | MS-31 | S Orrell | NO | NO | 1 | [10 empty] | 2 |  | 2020-08-20 | ASAP |  |  | Ready for Pick Up
[6 empty] | 42 | 554 | 474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 782 | 78 | 158
2020-08-24
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
1840 | Andrews Avenue Bridge Rehab | MS-6 | M Persons | NO | NO | 1 | 120 | [10 empty] | 15 | 2020-08-21 | 2020-08-26
19074 | VT Student Athletic Performance Center | PAP-01 | M. Jacobson | YES | YES | 22 | [6 empty] | 49 | [5 empty] | 2020-08-11 | 2020-09-08 |  |  | In Progress |  | All have been advised of Covid related delay at F.D. (8/11)
1873 | Reston Office Bldg 3 | PAP-15A | N Dowd | NO | YES | 3 | [6 empty] | 3 | [5 empty] | 2020-08-12 | ASAP |  |  | In Progress
1873 | Reston Office Bldg 3 | PAP-15 | N Dowd | NO | YES | 33 | [6 empty] | 43 | [5 empty] | 2020-08-12 | ASAP |  |  | In Progress
1840 | Andrews Avenue Bridge Rehab | MS-4 | M Persons | NO | NO | 1 |  | 6 | [10 empty] | 2020-08-19 | 2020-08-25 |  |  | In Progress
20001 | Thompson Hotel Savannah | MS-MU1 | L Bonilla | YES | NO | 5 | 7 | 9 | [9 empty] | 3 | 2020-08-18 | 2020-09-02 |  |  | In Progress
1771 | MD Project | MS-29 | M Kunz | NO | NO | 4 |  |  | 38 | [8 empty] | 10 | 2020-08-19 | 2020-08-27 |  |  | In Progress
1840 | Andrews Avenue Bridge Rehab | MS-5 | M Persons | NO | NO | 2 |  | 10 | [9 empty] | 3 | 2020-08-21 | 2020-08-28 |  |  | In Progress
19061 | Rosslyn City Center | MS-07 | M Jacobson | NO | NO | 1 | [8 empty] | 150 |  |  | 2 | 2020-08-18 | ASAP |  |  | In Progress
18105 | Potomac Shore MS | MS-05 | B Grizzard | YES | NO | 3 | 60 | 8 | [9 empty] | 10 | 2020-08-24 | 2020-08-26 |  |  | In Progress
[6 empty] | 75 | 187 | 33 | 38 | 0 | 0 | 0 | 95 | 0 | 150 | 0 | 0 | 43
2020-08-31
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-09-07
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 24 | 474 | 141 | 0 | 0 | 0 | 0 | 24 | 0 | 20 | 60 | 39 | 193
2020-09-14
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-09-21
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-09-28
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-10-05
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-10-12
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-10-19
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
2020-10-26
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-11-02
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-11-09
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-11-16
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-11-23
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-11-30
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-12-07
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-12-14
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-12-21
| Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-12-28
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-01-04
Job # | Name | Release # | PM | Loose Items | OutsourcePaint | Pt Dwgs | Zee / Hats/ Angles | Flashing | Coping | Splice Plate | Blade Screen | Perf | Plate Pannels | Frames | Strapping | Clips | Misc. | Est. MH | Rel-Date | Requested Ship Date | Shipped Date | Date Dif | Status | Shipped to Location | REMARKS
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Date Dif = IFERROR(IF([Job #]="","",DATEDIF([Rel-Date],[Shipped Date],"d")),"")
Date Dif = IFERROR(IF([Job #]="","",DATEDIF([Rel-Date],[Requested Ship Date],"d")),"")
Status = IFERROR(IF([Job #]="","",DATEDIF([Rel-Date],[Requested Ship Date],"d")),"")
Note on R130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: color samples
Note on Q251: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: panel plate attachment
Note on R258: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plate attachments-18 Tube End Caps-56
Note on R259: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vertical Tube End caps
Note on R284: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trespa Extrusions all 10' Sticks J-2100 (60) H-2100 (80) H-Slotted (23) Perforated Clouseres (10)
Note on R300: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Notched Z-Grit
Note on F323: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Waiting on color match approval to get the PO- per Andrea
Note on W451: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All the parts will be cut by end of the week, Tuesday they plan to begin the welds of the frames, Phil expects to have 5-10 full Units complete by the June 15 on-site date.
Note on R519: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: T-Brackets

## Job Specific
Job # | Job Name | Saleman | PM
1397 | CenturyLink Headquarters | ZM | PSR
1404 | Medstar Heart Institute | ZM | TH
1425 | 2155 Webster Street
1447 | Ballpark Square | ZM | DB
1475 | Barkley Elementary School | ZSM | LM
1476 | New Elementary & Middle | JR | TH
1477 | Hobby Airport Parking Garage | JR
1494 | Baptist Medical | ZM | LM
1532 | State Farm - Park Center | ZSM | DC
1534 | Birmingham Intermodal | ZM | AWF
1543 | OKC Municipal Courts Bldg | ZM | TG
1549 | Post Millennium Midtown | ZM | DC
1550 | New Office Bldg F | SKS | SKS
1551 | Laurel Library | ZM | TH
1552 | Duke Univ-Cameron Indoor | CCW | KP
1553 | Square 50 - Metal Panels | CCW | KP
1554 | Post South Lamar Phase II | ZM | DB
1555 | Waverly | ZSM | TG
1556 | Nextran Atlanta | ZM | JB
1557 | Allstate | JR | JR
1558 | The Carlton Hotel | SKS | SKS
1559 | Renaissance Hotel | SKS | KP
1561 | Loews Miami Beach | JR | KP
1563 | Surfstyle | SKS | KP
1565 | Piping Rock Health | SKS | TH
1568 | Auburn TownePlace Suites | CCW | KP
1569 | 120 Ocean Dr Penthouse Rem | ZM | KP
1571 | Dadeland Mall Columns | SKS | BR
1572 | Sanders YMCA | SKS | DC
1573 | Plant McDonough | SKS | JR
1574 | Eastern Maine Medical-Canopy | ZSM | JH
1577 | BPPR Urban Hub | JB | JB
1582 | Gray Construction SE Office | ZM | BR
1585 | Kempsville Comm Rec Ctr | ZSM | JH
1590 | Cambria Hotel & Suites | ZM | BR
1591 | Mt San Antonio College | ZSM | DW
1593 | Angler's Hotel | ZM | AWG
1594 | Midtown Plaza Tower | SKS | DC
1596 | OCC Coulter Library | ZM | JR
1597 | Mickey Leland College Prep | CCW | JR
1598 | Duke Univ-Wallace Wade Tow | ZM | DC
1599 | Dakota Crossing | ZM | KP
15101 | 2700 Colorado Ave | CCW | BR
15102 | ATT- Camp Creek | ZM | TG
15103 | UF Health - 92 Bed Patient | ZM | TG
15105 | Sitbon Residence | ZM | DC
15106 | Eastern Maine Med Ctr | SKS | DC
15107 | Henry Mayo Newhall Hospital | CCW | JB
1601 | 230 Lincoln Road | ZM | JR
1602 | Comcast Office Bldg | SKS | DC
1603 | FSU - Doak Campbell Stadium | ZM | AWG
1604 | U Health Gables | ZM | JH
1605 | Renaissance Hotel Legacy | ZM | PR
1606 | Gables Auto Vault | ZM | TG
1607 | Muse | SKS | BR
1608 | GSU Military Science Bldg | SKS | SO
1609 | J.E. Edmonds Elementary | SKS | JB
1612 | UF- O'Connell Ctr Expansion | JA | KP
1613 | Rosa Jackson Community Ctr | ZSM | DB
1614 | Seattle SR99 Tunnel Project | ZSM | LM
1615 | USC - Student Health Center | ZM | SW
1616 | Roxy Theatre | ZM | JB
1620 | Reeves Young Corporate | ZM | PR
1623 | Five Points Marta Station | ZSM | PR
1624 | Bank of America - Turkey Creek | CCW | SO
1625 | Crittenden Middle School | JA | TM
1626 | Skip Viragh Outpatient Center | ZM | JH
1630 | Overton Office Bldg | CCW | BR
1631 | MSM Hugh Gloster Pavilion | CCW | JH
1632 | Cornell Univ CVM Class | CCW | LRM
1633 | Grifols E750 ADMIN Bldg | ZM | DB
1634 | Stardust West | ZM | SO
1635 | 2600 Douglas | SKS | DC
1636 | Volvo Customer Experience Ctr | SKS | JWB
1637 | DIA Parking Garage | SKS | SO
1638 | 1200 South Figueroa | ZM | BR
1639 | Piping Rock Health | ZM | JH
1640 | M Residences | CCW | JWB
1641 | Burke Co Teaching & Learning Ctr | CCW | JH
1642 | Free Chapel Church Façade | CCW | JWB
1643 | Schaeffler USA: New Office Bldg | ZSM | JWB
1644 | OMNI Hotel | ZSM | PR
1645 | AVA Studio City - Leasing Ctr | ZM | JH
1646 | STEM Building at BPCC | ZM | JH
1647 | 4004 Perimeter Summit | ZSM | TG
1651 | The Bristol | CCW | JH
1652 | Wellstar Child Care Center | ZM | DB
1653 | AHS Canopy | ZM | JB
1654 | Echo Brickell | ZSM | JWB
1655 | Brookwood Visitors Parking Deck | SKS | MJ
1657 | CHOA Scottish Rite Vertical Exp | ZSM | SO
1660 | United Therapeutics | ZM | JH
1661 | Avalon Bldg 8000 | ZM | BR
1662 | Avalon Phase 2 - Retail | SKS | JWB
1663 | Hard Rock Tampa | SKS | JLJ
1664 | New Brighton Contral Station | ZM | DC
1665 | Peachtree & 3rd | RL | MJ
1666 | FHSU Institute for Applied Tech | ZM | PR
1667 | 1213 NP Ave | RL | MJ
1668 | Ballston Quarter- Residential | RL | MJ
1670 | LA Capitol Federal Credit Union | ZM | BR
1671 | Coral Springs Municipal | ZSM | MH
1672 | Ballston Quarter- Retail | SKS | MK
1676 | Carter G. Woodson Library | ZM | SH
1677 | Portner Place- Wing A | RL | JWB
1678 | 1441 U Street | ZM | MH
1679 | SAS Building A | ZM | MH
1680 | District 36 | ZM | MJ
1681 | Mattress Firm at Waverly | SKS | JLJ
1682 | 800 Lincoln Rd | JV | JB
1683 | Mountain lakes Medical Center | KA | MK
1684 | TRU Hotel by TRU | KA | PR
1685 | Waterton Residential | KA | SH
1686 | USD 266 Maize Early Childhood | RL | MK
1687 | Mercedes Benz Stadium | RL | MJ
1688 | 801 Lincoln Rd | ZSM | MK
1689 | Union Market- 1270 4th St | SKS | JH
1690 | Bannkkburn | ZM | BR
1691 | Ashland Ave-Change Order | RL | MK
1692 | Member One | BR | BR
1693 | Four Seasons Hotel | SKS | SO
1694 | Choctaw nation of Oklahoma | ZM | MH
1695 | Academies of Loudoun | ZM | TG
1696 | North & Line | ZM | JB
1697 | Free Chapel Church - Chapel | CCW | TM
1698 | Miami Dade College Bldg 6 | ZSM | JB
1699 | Waverly Bldg K | KA | MH
16100 | Paraiso Bay | JV | SO
16101 | Cleveland Clinic CUP Connector | ZM | MK
16102 | NU Hogan Dock | ZSM | PR
16103 | Lakeview | RL | MK
16104 | Alan Wire Company | TG | TG
16105 | River Center Branch Library | RL | MJ
16106 | Turner Exterior Enhancements | JA | TM
16107 | Tru Hotel -York PA | CW | JH
16108 | Loudoun Station Parking Structure | KA | SH
16109 | 5707 Waterford - Burger King HQ | CCW | JH
16110 | Northside Midtown MOB & PD | ZSM | TM
16111 | Chipotle #2571 Waverly | CCW | MK
16112 | Palm Springs Block B | JV | SO
16113 | Lynchburg Replacement Panels | RL | TH
16114 | Army Cyber Command Headquar | CCW | TG
16115 | Mercedes Benz USA | ZSM | JH
16116 | Advia Credit Union | SKS | SO
16117 | The Hubb | RL | MJ
16118 | UT Screen Walls | RL | TH
16119 | CHOA- Town Center MOB | MD | JB
16120 | CHOA- Pediatric MOB | ZM | TG
16121 | 300 Riverside | ZM | TG
16122 | Avalon Hotel & Conference Ctr | ZM | JH
1701 | Modera Buckhead | SKS | JB
1702 | Dominion Workplace | ZM | PSR
1703 |  | CCW | JH
1704 | 11 Stone Street
1705 | Cape Girardeau Police Station | ZM | TH
1706 | Our Lady of the Lake Children | RL | MH
1707 | Broward Addiction Recovery Ctr | ZSM | TH
1708 | UNG Convocation Center | SKS | TH
1709 | Mannington Mills Office Exp | SKS | MH
1710 | McLarty Nissan | CW | JB
1711 | Danville Community College | JA | BR
1712 | CCTC Academic Bldg | KA | TH
1713 | UF Innovation Hub - Phase 2 | KA | JB
1714 | TMH M.T. Mustain ICU | ZSM | TM
1715 | Kentucky International Convention | CCW | SO
1716 | 725 Ponce | SKS | TH
1717 | Beacon Telemundo | CCW | MH
1718 | HudsonAlpha | SKS | MK
1719 | L'Enfant Plaza Office Bldg | ZSM | TM
1720 | Woodfield Mall Dining Pavilion | SKS | SH
1721 | Aventura Mall | ZSM | JFB
1722 | 1201 N LaSalle | SKS | MK
1723 | Suncoast Credit Union | SKS | TH
1724 | Atrium Village Phase I | SKS | JB
1725 | Hard Rock Tampa- East Tower | RL | TH
1726 | RagingWire VA3 Data Center | ZM | DC
1727 | RagingWire VA3 Data Center | ZM | JB
1728 | Parkview on Peachtree | ZM | JB
1729 | LIV Cleo Apartments | CW | JFB
1730 | Reston Hospital Ctr | ZM | JFB
1731 | Coral Springs Municipal -Clerestory | CCW | SH
1732 | Arizona General Hospital ER | SKS | MK
1733 | UTC - CIB | KA | SW
1734 | Old Fourth Ward | ZSM | JB
1735 | 2300 North St NW Roof | ZSM | PSR
1736 | McCrory Senior Apartments | JV | SO
1737 | The Spark | RL | MJ
1738 |  | RL | MJ
1739 | West Hollywood Park-Phas 2
1740 | BRCH - Lynn Cancer Institute | ZM | TH
1741 | 723 Lincoln Lane | ZSM | CJ
1742 | The Highline | SKS | MK
1743 | United Therapeutics- D-DOMAL | ZM | SO
1744 | Ripley East | ZM | BR
1745 | 2600 Douglas Rd (ceiling) | ZM | JH
1746 | Kovach Southmore | SKS | JB
1747 | BART El Cerrito Del Norte | DC | DC
1748 | Echo Brickell - Garage | RL
1749 | Rite Aid - Long Beach, CA | SKS | MK
1750 | Mountain America Credit Union | KA | JH
1751 | Hyatt Place Hotel | KA | SJW
1752 | Roper St Francis Medical Office | KA | JH
1753 | 7000 Central Pkwy Lobby | JV | CR
1754 | Buffalo State College Alumni | ZSM | CJ
1755 | 8600 Wilshire Blvd Mixed Use | JV | SO
1756 | NGMC Outpatient | RL | TH
1757 | District #8 Middle School | CW | Jbarter
1758 | Oakbrook Theater Canopy | RL | MJ
1759 | Georgia Proton - Ph 1 & 2 Restart | RL | MK
1760 | 676 N LaSalle | ZSM | MK
1761 | DEF LLC | RL | Justin
1762 | Letner United | RL | MJ
1763 | Palomar | ZM | DB
1764 | Mary Street | SKS | MK
1765 | Roosevelt eSTEM Academy | SKS | MK
1766 | Kopolow Bldg & Site Renovation | JA | SW
1767 | Holiday Inn Express - NOLA | RL | MJ
1768 | The Charles | ZSM | CT
1769 | 520 West 20th Street | ZM | PR
1770 | NE Methodist Hospital | JV | MJ
1771 | MD Project | KA | Jbraden
1772 | Central Campus Health Center | ZM | EE
1773 | The GEO Group Corporate HDQ | JA | CR
1774 | Camden Office Tower | ZSM | EE
1775 | Baker Buick GMC Panel Replace | JV | Jbraden
1776 | Rise at Riverfront Cxg- Hotel | LR | AY
1777 | Grant Park Zoo | ZM | Jbarter
1778 | Choctaw - Vision Enclosure
1779 | One Daytona Blvd Column | TG | TG
1780 | Lil Drug Store Products New Fac | LG | AY
1781 | Rise at Riverfront Cxg- Residential | RL
1782 | UCF Trevor Colbourn Hall | ZM | Jbarter
1783 | Starlight Elementary School | SKS
1536 | NGHS | JA
1785 | Vasser Brothers
1784 | Atlanta Dairies
1786 | 45 L Street
1787 | Home Depot Backyard Escalator
1788 | Baptist Beaches
1789 | Wheaton Library
1790 | Hascom Primary School
1791 | OMNI Hotel Louisville
1792 | ICPH Campus Infrastructure
1793 | Miami World Center
1794 | Project Raven
1795 | Buffalo Psych Center
1796 | 4040 Wilson Blvd
1797 | UAB Proton Therapy
1798 | Central Records Complex
1799 | Memorial To Peace
17101 | The Boro - A1
17102 | The Boro - A2
17103 | The Boro - A3
1800 | Tyler's PE Jobs
1801 | Metro Health Parking Garage
1802 | Ho Chunk Gaming
1803 | KONAR Flex WX Building
1804 | Concord Mills Mall
1805 | MET Square Phase 2
1806 | Comstock Reston Metro Station
1807 | Virginia Western Community College
1808 | F-35A ADAL Field Training
1809 | Aventura Mall Remakes
1810 | Wanda Vista Hotel
1811 | State Farm Park Center Phase II
1812 | Nextran Replacement Panels
1813 | MSM Gloster Renovations
1814 | ESU Market Street Residence Hall
1815 | Riverside University
1816 | Drive Wise Auto Sales
1817 | Missouri Ridge School
1809 | Aventura Mall Remakes
1813 | MSM Gloster Renovations
1816 | Drive Wise Auto Sales
1818 | General Dynamics
1819 | EAMC Cancer Center
1820 | SMH-West Parking Garage
1821 | One Alliance Little Alley
1822 | Echo Brickell Replace Pnl
1823 | Biola Replacement
1824 | Noho West
1825 | Gateway of Pacific
1826 | Porsce Design Tower Replacement
1827 | AC Hotel Replacement Panels
1828 | Town Center at Boca Raton
1829 | The Living Building at Georgia Tech
1830 | 15th & Market
1831 | Renaissance Hotel Replacement
1832 | 150 5th Avenue
1833 | University of Maryland
1834 | Jeff Smith Chevrolet Replacement Panels
1835 | Aventura Mall Replacement Panels
1836 | Miami Heat Practice Court
1837 | Prairie Early Childhood Center
1838 | Fairfield Area Library
1839 | Western Nebraska Community College
1840 | Andrews Avenue Bridge Rehab
1841 | HDBY - SponsorZone
1842 | Bangor Savings Bank
1843 | Project Viper
1844 | VT Corporate Research Ctr
1845 | Mt. Harmony Baptist
1846 | Gables Auto Vault Remakes
1847 | Waverly Tile Replacement
1848 | Stryker Sports Indoor Facility
1849 | GA Tech Invention Studio
1850 | Broadway Residences
1851 | GC America
1852 | Mission Outpatient Center Replacement
1853 | ASU Sun Devil Stadium
1854 | Calexico Stadium
1855 | Douglas Emmet
1856 | Greene County HS & MS
1857 | Le Meridien
1858 | Arthrex Office Building
1859 | MCCNO Linear Park
1860 | Radford University - Curie Hall
1861 | UIC Student Housing
1862 | SCAD-ATL Student Housing
1863 | Project Morning Hornet
1864 | GOAA- South Terminal C
1865 | VT Solar
1866 | 3034 Grand Avenue
1867 | Baptist Hilton
1868 | Colony Square Bldg 400
1869 | Bank of the Ozarks HQ
1870 | Edgewood Recreation Ctr
1871 | Element Southpark
1872 | Carmax - Pleasant Hill
1873 | Reston Office Bldg 3
1874 | Twelve24
1875 | Piedmont Pinewood Ctr
1876 | APS Tag Academy
1877 | The Edison Pembroke Pines
1878 | Towers Crescent Replace
1879 | Essentia Wellness Center
1880 | Project Wildcat
1881 | The Plaza Coral Gables
1882 | Nueva School Bay Meadows
1883 | 1050 17th Street
1884 | Texas Rangers Ballpark
1885 | 24 Hour Fitness Homestead
1886 | 24 Hour Fitness Miami
1887 | Lauderdale Imports
1888 | East Forest Park Library
1889 | Wellstar Acworth ASC
1890 | 1688 Meridian
1891 | 1781 Peachtree
1892 | Halo
1893 | Nova Residence Hall
1894 | UCF Replacement
1895 | River Laning
1896 | North Hills Tower IV
1897 | IAAPA World Headquarters
1898 | Avalon 10000
1899 | Upper School for Boys
18100 | Port of Miami Terminal B
18101 | North Cobb Library
18102 | Gulfstream Service Ctr E
18103 | Moving in the Spirit
18104 | Garco Mill Entertainment
18105 | Potomac Shore MS
18106 | Mercedes Screenwall
18107 | Felsenthal Residence
18108 | UAB Residence Hall 2020
18109 | West Riverside ES
18110 | Jackson Rehab Building
18111 | BHSF Plantation MOB
18112 | NHA 1-2
18113 | 1111 Brickell
18114 | 120 Ocean Drive Flashing
18115 | The Millennium on LaSalle
18116 | Northwinds Summit 3000
18117 | 699 14th Street
18118 | Gemini MS Add & Remodel
18119 | Prince George County FTTC
18120 | Owens Murphy JLR
18121 | UM Proton Therapy Center
18122 | 1470 Owens Parking
18123 | Penn State Heister Street
18124 | F21 at Atlantic Station
19001 | Hard Rock Porte Cochere
19002 | Vestavia Medical Plaza
19003
19004 | Bangor Savings Bank Mat
19005 | MTAPD District 9 Police
19006 | Georgia Aquarium 2020 Exp
19007 | BLVD at Lenox
19008 | Palestine Wheatley HS
19009 | W Nashville
19010 | Star Metals Office
19011 | DC15
19012 | Hyatt PL Perimeter Mall
19013 | Aventura Charter
19014 | CarMax - Palm Desert
19015 | Halo
19016 | Rush Univ Medical Ctr NAB
19017 | MSM Gloster Remakes
19018 | Jack London Sq Parcel F2
19019 | Ken's Foods Office
19020 | American Express
19021 | The Works Parking Garage
19022 | UAB McCallum Phase I
19023 | Oakmead Parkway
19024 | Holy Cross Recreaton Ctr
19025 | 1105 West Peachtree
19026 | Phipps Plaza H & T
19027 | Costex Tractor
19028 | GCS College Damaged Panel
19029 | 60 Charlton Ave
19030 | 1105 West P'Tree Office
19031 | 1105 West P'Tree Condo
19032 | 1105 West P'Tree Hotel
19033 | 1105 West P'Tree Parking
19034 | Hyatt Place Titusville
19035 | Phipps Plaza Office
19036 | Phipps Plaza Anchor
19037 | Phipps Plaza Hotel
19038 | Phipps Plaza Parking Deck
19039 | Project Viper Elevator
19040 | RWC 4 - ECR & Diller
19041 | WPUSD - Twelve Bridges HS
19042 | 1300 4th Street NE
19043 | Synovus Data Center
19044 | PTC Southern Beltway
19045 | Rio STEAM K-8 Campus
19046 | Missouri Ridge School
19047 | Project Charisma
19048 | ChemTreat Ashland New Lab
19049 | VA Aquarium Marsh
19050 | SMH-Oncology Tower
19051 | WestStar Tower
19052 | Three Ballpark Center
19053 | Whole Foods Nashville
19054 | Tift RMC-ED & Patient Twr
19055 | Actionpak and Resintech
19056 | Turnberry Ocean Club
19057 | Bixy Dawes City Hall
19058 | Reston OB 2 Garage
19059 | Aflac Site Security
19060 | Dadeland Mall W Kendall
19061 | Rosslyn City Center
19062 | HUSD STEAM Building
19063 | Nextran Truck Ctr Damage
19064 | The Osprey
19065 | UNG Convocation Replace
19066 | Emory Johns Crk Hospital
19067 | Portner Place Soffit
19068 | 1221 Brickell
19069 | Rosemary Tower
19070 | Glen Lennox Office Bldg
19071 | Ascent Gulch
19072 | Oak Grove R&G
19073 | UM Student Rec Center
19074 | VT Student Athletic Performance Center
19075 | Excelsior Mill
19076 | Charlton Screen Wall
19077 | Sawmill Station Shopping Center
19078 | UPMC Hillman Cancer Center
19079 | International African American Museum
19080 | Monad Terrace
19081 | EIE380 F35 Missile Maintenance Facility
19082 | Gulfstream
19083
19084 | Fulton County South STEM School
19085 | Bellyard at the Interlock
19086 | Cedarburg High School
19087 | Harder Elementary School
19088 | Besty Ross Canopy
19089 | Methodist Hospital
19090 | SCAD Victory Drive Student Housing
19091
19092
19093
19094
19095
19096
19097
19098
19099
19100
19101
19102
19103
19104
19105
19106
19107
19108
19108
19109
20006 | The Adley At City Springs
20002 | Coca-Cola Hangar
20015
20036
20001 | Thompson Savannah Hotel